## Slide 1: Subprogramme4 - Data and Statistics
Accountability and Programme Performance Review Meeting
Mid-Year Programme Status Report for 2025
Theme: “Accelerating results by reflecting on progress, opportunities and challenges by midyear of 2025”
19 June 2025

## Slide 2
Knowledge products
Advisory Service
Capacity Building
1
Members of ECA produce and disseminate comparable economic statistics
Towards integrated Geospatial information framework
Overview 2025-
Data and Statistics
Improved CRVS System
  Use of Python and R coding, Deployment of digital tools and applications for census operations
  Applying geodesy in governance, economic planning, and sustainable development.
  Technical and institutional skills in Integrating geospatial technologies in Censuses
  Technical standardization in CRVS
Towards digital transformation and modernization of statistical systems
Successful transition to the 2008 SNA framework - Guinea and Sierra Leone
CRVS strategic plans and policy frameworks in developed in South Sudan and Burundi
Preliminary draft of the national action plan for implementing the UN Integrated Geospatial Information Framework (UN-IGIF) endorsed-Mali
Sstatistical harmonization enabling GDP estimation and CPI development in Eritrea
Togo submitted its first National Quality Assurance Framework in statistical systems to Parliament
1 National Mapping Agency
20 NSOs
193
Experts
CoF: Malawi, Botswana, Kenya, Rwanda, Nigeria, Ghana, Ethiopia, Comoros Burkina Faso, Burundi Other: Togo, South Sudan, Guinea, Benin, Namibia, Sierra Leone, Eritrea, Madagascar, Eswatini, Lesotho
Countries Reached
Target audience
Changes observed
Capacities developed
Notes: Speaking points for the DES.
The African Centre for Statistics under SP4 is contributing to the objective of production, dissemination and use of credible data, statistics and geospatial information at the national, regional and global levels for evidence-based policy and decision-making. In the reporting quarter, the SP reached 16 countries with various data and statistical technical, advisory and capacity building supports. The SP provided advisory services for Cameroon, Mali, Burundi, and Rwanda on integrated geospatial information framework that resulted in the development of Country Action Plan and incorporated it in their national polices and strategies. Tailed made capacity building training were provided to data experts and statisticians in Nigeria, Malawi, Uganda and Namibia with the aim of modernizing the vital statistical production process using the R method. The technical knowledge and skill of the National Statistical Offices of the respective countries in the production and utilization of CRVS process using R method improved. The technical support to modernize the Census Monitoring tools and Dashboard improved the survey process utilization and the application of up-to-date survey monitoring services in Angola, Benin and Burundi. The SP organized consultation workshop to enrich the content of the Draft E-Census handbook and pertinent insights were incorporated to expand on a digital census business model through increased use of technological and methodological innovations. Ongoing technical advisory support on Economic Accounting were provided. Participants, including statisticians and data experts from various National Statistical Offices (NSOs), capacitated their skills how AI-driven technologies can streamline operations, improve data accessibility, and automate complex tasks. The technical support provided practical examples of how African NSOs could integrate AI into their work, reducing manual processes and advancing their capacity for innovative data analysis. The event highlighted the transformative potential of generative AI for modern statistical practices and set the stage for future discussions on this cutting-edge topic. The SP is supporting Eritrea with Economic Accounting data sets including updating macro-economic statistics and data. Ongoing activities including online update of price watch data along with other corresponding data sets is in progress. ECA is designated as data verification client for the East African Community Programme (EAC). In the reporting quarter ACS provided verification support on broad data sets including geospatial information, economic and demographic statistics indicators to National Statistical Offices of Kenya, Rwanda and Tanzania. The verification process was followed by compiling and submitting reports to the World Bank which resulted in access to Disbursement Fund for the member states.

## Slide 3
What
How
Where
Evidence
Result Area 2: Members of ECA produce and disseminate comparable economic statistics
2
2 member States successfully Transitioned to the 2008
Guinea and Sierra Leone
Sierra Leone fully transitioned to the 2008 SNA.pdf ; https://statics.teams.cdn.office.net/evergreen-assets/safelinks/1/atp-safelinks.html
Conducted regional and in-country training workshops for national accountants and statisticians
Supported improvements in source data quality and availability- household and business surveys administrative data systems
Promoted peer learning and South-South cooperation- African Group on National Account (AGNA)
Specialized Technical Groups (like STG-4 on National Accounts), PARIS21, Regional Economic Communities (RECs- ECOWAS, AFRISTAT), and collaboration with UN agencies (UNCTAD,) involved in knowledge sharing and peer learning

## Slide 4
What
How
Where
Evidence
Result Area1: Towards digital transformation and modernization of statistical systems
3
Mobile Statistical Platform (MSP) developed as a significant advancement in data accessibility and analysis
The App Store and Google Play.
https://github.com/tech-acs/ecastats_app The app will soon be available for download on both the App Store and Google Play.
Initiated based on SLT retreat decision
Conceptualized and designed by ACS
Collaborative engagement with statisticians and IT experts
Agile approach: daily stand-ups & weekly reviews
Built on ACS innovation: Census Executive Monitor (Zambia & Zimbabwe)
Integrated with ECA Stats portal via API (Application Programming Interface) for real-time update

## Slide 5
Performance Metrics
________________________________________________________________________________________________________
4
RA | IoA | Milestones (including deliverables as applicable) | Target | Actual as of Q4 | Status % | Status
 |  | Q1 | Q2 | Q3 | Q4 | 
RA1 | Number of members of ECA that implemented the road map on digital transformation and modernized official statistics (cumulative) | Advisory services to South Sudan on strengthening the governance of the national statistical systems | Togo validates the National Quality Assurance Framework (NQAF) in statistics to improve quality of official statistics including administrative data | Cameroon has published the turnover index produced from administrative data | National Statistical System (NSS) maturity model assessment questionnaire validated | 
RA2 | Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics (cumulative) | Advocacy on strategies to accelerate transition to 2008 SNA | DRC publishes data according to 2008 SNA (The Milestone was set to support DRC, while DRC is in progress the SP achieved progress for Siera Leone and Guinea. Guinea republic announced its transition to the SNA 2008 in January 2025 while Sierra Leone announced transition to SNA 2008) | Advisory missions to 2 countries (Togo, Eritrea) on migration to the SNA 2008 or SNA 2025 | Comoros or Madagascar publish data according to 2008 SNA | 

## Slide 6
Performance Metrics
________________________________________________________________________________________________________
4
RA | IoA | Milestones (including deliverables as applicable) | Target | Actual as of Q4 | Status % | Status
 |  | Q1 | Q2 | Q3 | Q4 | 
RA3 | Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) | A regional training workshop on enhancing geospatial information management for Mozambique | National capacity development workshops for Comoros, Eswatini | National stakeholder's forum for Mali | Update of the national geospatial datasets | 
RA4 | Number of member states adopting innovative technology applications in CRVS systems (Non-PPB) | South Sudan develops a CRVS plan | Expert Group Meeting for Registrar Generals of 54 African countries to adopt a common continental ICT asset for CRVS | Burundi develops a CRVS Strategic Plan | South Sudan and Burundi CRVS digital system operational | Will be achieved 23-27 June

## Slide 7
5
Contribution to Sustainable Development Goals
__________________________________________________________________________________________________________________
Budget expenditure
$329,275.36
8.1;8.9
16.6; 16.9;16.10
17.18
17.19
SDG
SDG Target
Technical support for the development and deployment of digital census tools (e.g., dashboards) in countries like Guinea and Benin, mobile applications
$74,121.04
$31,109.05
$221,135.14
Modernizing national accounts systems across Africa, addressing outdated economic data frameworks, data quality gaps, and weak institutional capacities
Strengthening Integrated Geospatial Information Systems for Sustainable Development and Enhanced Governance in Africa:
Strengthening Civil Registration and Vital Statistics (CRVS) Systems through Applied Research, Digital Innovation, and Capacity Building in Africa
SP Contribution
17.18; 17.19; 17.6; 17.9
9.1;9.C
11.3
16.19

## Slide 8
ENVIRONMENTAL SUSTAINABILITY
DISABILITY INCLUSION
HUMAN RIGHTS
Applied LNOB approach to assess disparities in birth/death registration by gender, location, income & ethnicity.
Promoted inclusive consultations with women-led institutions & gender ministries in geospatial initiatives.
Assessed inequalities for vulnerable groups, incl. persons with disabilities, using DHS/MICS data
Supported the Water-Energy-Food Nexus analysis targeting environmental sustainability in rural transformation planning
Facilitated improved land use, urban planning, and disaster risk reduction deploying geospatial reference systems,
CRVS advances SDG 16.9 by promoting universal birth and death registration
Incorporated legal protections and rights-based approaches to identity documentation.
Cross-cutting issues
________________________________________________________________________________________________________
GENDER
6

## Slide 9
Launched African E-CRVS Shared Asset (ACSA), published digital solutions framework, piloted web-scraping in GDP estimation tools
Implementation Challenges/
Lessons
Solution
7
Reflections
_________________________________________________________________________________________
Limited institutional capacity and financial constraints
Weak integration and outdated data frameworks)
High cost and complexity of digital transformation and lack of standardized,
Capacity-building is effective when combined with national ownership and sustained technical support
Strategic frameworks and country-led implementation strengthen systems and drive ownership
Shared solutions and innovation hubs can reduce costs and duplication while improving quality and consistency
Applied research and South to South are crucial to improve statistical practice and inform policymaking
Phased technical support
Established GDP taskforces
Leveraged RCO coordination
Leveraged the use of South-to-South cooperation

## Slide 10
8
New evidence for analysis (if any)
_________________________________________________________________________________________
Digital Transformation & Innovation:
Expanding shared digital platforms (e.g., African E-CRVS Shared Asset), ECA Mobile Application, AI integration, and secure, interoperable tools.