## Slide 1: Subprogramme 4: Data and Statistics
Accountability and Programme Performance Review Meeting
Mid-Year Programme Status Report for 2026
Theme: “Enhancing Joint Delivery for Improved Results after UN@80 Reforms”
17 – 19 June 2026

## Slide 2
1
17 Countries Reached
Target audience
CoF: Rwanda,
Sao Tome & Principe, Mozambique
Other: Comoros, Gabon, Ghana, Eritrea, Lesotho, Malawi, Mali, Namibia, Seychelles, Sierra Leone, Madagascar, Lesotho, Togo, Kenya
RA2: Towards integrated Geospatial information framework
RA3: Improved CRVS System
RA1: Produce and disseminate comparable economic statistics
Overview of subprogramme work in 2026
Rwanda: Produced 2025 Vital Statistics Report with enhanced data quality and timeliness
Eritrea: advancing evidence-based water, land and environmental planning by developing an IGIF-based roadmap
Mali: Strengthening the policy framework for integrated geospatial information management
25 MS integrated into African Continental Input-Output (AfCIOT)
Capacities Developed
2 National Mapping Agencies
17 NSOs
230
Data & Statistical Experts
2 Line Ministries
RA4: Strengthened statistical product innovations for enhanced policy linkages
Utilizing automated tools for Vital Statistics (Namibia)
Producing and reporting agricultural statistics across the full production cycle
Use of Reproducible Analytical Pipelines (RAPs) using R (Malawi).
NA and BoP compilers’ capability to plan and manage transition to BPM7 and 2025 SNA
Leveraging AfCIOT and TiVA outputs for economic policy formulation
Use of Earth Observation data for agricultural statistics and crop monitoring
Changes Observed
2
Notes: This slide presents an overview of the Subprogramme’s work in 2026, focusing on strengthening integrated statistical, geospatial, and sectoral statistical systems across member States. The work is organized around four main Result Areas: improving the production and dissemination of comparable economic statistics; advancing implementation of the Integrated Geospatial Information Framework (IGIF); strengthening Civil Registration and Vital Statistics (CRVS) systems; and promoting statistical innovation to enhance policy relevance and decision-making.
The Subprogramme reached 13 countries in total, including targeted support to three ECA priority countries: , Sao Tome and Principe, Mozambique, and Rwanda, as well as 10 additional countries under regional and thematic interventions. Key stakeholders engaged include 13 National Statistical Offices, 161 data and statistical experts, and representatives from two-line ministries and two national mapping agencies, reflecting a broad-based effort to strengthen national statistical ecosystems.
Significant capacity development was achieved across multiple technical domains. In national accounts, staff in Eritrea enhanced their ability to apply standardized methodologies for GDP compilation, including improved use of production approaches, classification systems, and valuation techniques. In geospatial statistics, Eritrean participants strengthened practical skills in generating geospatial insights through the application of GIS and remote sensing tools for land, water, and environmental analysis. In CRVS systems, Togo and Rwanda improved operational efficiency through the use of standardized and automated processes for the production of annual Vital Statistics Reports, enhancing timeliness, consistency, and reliability of demographic data. In São Tomé and Príncipe, methodological capacity was strengthened in the design and implementation of tourism enterprise surveys, improving the quality and usability of sectoral statistics.
These capacity gains have led to clear and observable changes in practice. In Eritrea, there has been a notable transition from foundational awareness to the applied and integrated use of GIS and remote sensing under IGIF Pathway 8. Staff are now actively applying geospatial tools to real operational tasks in land, water, environmental, and cadastral management, reflecting a shift from theoretical understanding to practical, decision-oriented use. Across interventions, there is also increased institutional readiness to adopt standardized statistical methods, improved data production efficiency, and stronger integration of geospatial and statistical systems to support evidence-based policymaking

## Slide 3
What
How
Where
Evidence
Result Area 4: Strengthened statistical product innovations for enhanced policy linkages
________________________________________________________________________________________________________
3
Introduced a Statistical Disclosure Control (SDC) module under census technical assistance to support NSOs in safely anonymizing and releasing census microdata
Developed an internal Statistical Disclosure Control (SDC) methodological handbook based on the sdcMicro R package along with the SDC reference material
Adapted the handbook to the African census context, strengthening its mathematical rigor and practical implementation guidance
Incorporated intuitive examples to enhance NSO staff understanding of the underlying SDC theory and application
Trained 8 ZAMSTATS experts on the Statistical Disclosure Control (SDC) module
Strengthening data protection and confidentiality for the secure, wider dissemination of high-quality census microdata
Zambia (ZAMSTATS)
Zambia SDC Pilot

## Slide 4
What
How
Where
Evidence
Result Area 3: Improved CRVS System
________________________________________________________________________________________________________
3
Accelerating vital statistics reporting through digital technology
Rwanda
Technical support and advisory services to production of the 2025 vital statistical report:
  Trained 22 government Officials to use programming language for data processing
  Adapted the CRVS R pipeline with country 2025 administrative records on births, deaths and marriages
  Enhanced quality and content of statistical tables. advisory services
  Strengthened national capacity on innovative communication and messaging of vital statistics
  Partnership: EAC, Vital Strategies, Bloomberg Inc
2025 Rwanda Vital Statistics Report

## Slide 5
Performance Metrics*
____________________________________________________________________
RA | IoA | Milestones | Target | Actual as of Q4 | Status % | Status
 |  | Q1 | Q2 | Q3 | Q4 | 
RA1 | Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics | Workshop on the new System of National Accounts and the new Balance of Payments Manual | A country, that was not previously using SNA 2008, has produced a new series in accordance with SNA 2008. | Validation of the results for the new 2008 series for at least one country. | A country, that was not previously using SNA 2008, has published a new series in accordance with SNA 2008 | 
RA2 | Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework | Capacity-building training on statistical and geospatial insights. | Domesticated Action Plan for an Integrated Geospatial Information Framework (UN-IGIF) drafted | Priority Strategic Pathways (Such as Governance, Data, Standards, Capacity) assessed | UN‑IGIF Country-Level Action Plan developed and endorsed for Verifications | 
4
Notes: This slide presents the key performance metrics structured around two Results Areas under the programme.
For RA1, the focus is on strengthening the capacity of member States of the United Nations Economic Commission for Africa to adopt and apply internationally recommended statistical standards, particularly the 2008 System of National Accounts and its extensions in economic statistics. This area sets the foundational objective of improving harmonization and comparability of economic data across countries.
For RA2, the emphasis shifts to the application of at least one strategic pathway of the United Nations Integrated Geospatial Information Framework. The milestones are sequenced across the quarters: in Q1, capacity-building training on statistical and geospatial insights was conducted; in Q2, work began on drafting the domesticated IGIF Action Plan; in Q3, support is focused on implementation of IGIF; and in Q4, continued support is provided with particular attention to SP2 and SP8 implementation. Overall, the slide highlights a progression from capacity building and planning toward implementation and targeted technical support.

## Slide 6
Performance Metrics*
____________________________________________________________________
RA | IoA | Milestones | Target | Actual as of Q4 | Status % | Status
 |  | Q1 | Q2 | Q3 | Q4 | 
RA 3 | Number of members of ECA adopting innovative technology applications in civil registration and vital statistics systems (cumulative) PPB 2026 | CRVS R Pipeline Training | Validated statistical tables produced using R Pipeline | Draft vital statistics report | CRVS validated reports | 
RA 4 | Number of statistical products developed for use in policy formulation, monitoring and dissemination (cumulative) | Interactive integrated statistical portal developed | Feedback gathering survey launched | Mobile version of the portal developed | User engagement survey reports for policy use | 
4
Notes: For RA3, the focus is on increasing the number of ECA member states adopting innovative technology applications in civil registration and vital statistics systems. Throughout Q1 to Q3, the key activity is the delivery of CRVS R Pipeline trainings, which build technical capacity across member states. In Q4, the emphasis shifts to validating and consolidating the training outputs through validated CRVS reports. Overall, this reflects a progressive capacity-building approach that moves from training to validation and evidence generation, and the status remains in progress. For RA4, the objective is to enhance the development and use of statistical products for policy formulation, monitoring, and dissemination. Across Q1 to Q3, efforts are centered on developing an interactive integrated statistical portal, which serves as a key dissemination and analytics platform. In Q4, the focus moves toward assessing utilization through user engagement survey reports to support policy relevance and uptake. This ensures that the technical outputs are not only developed but also actively used by end users for decision-making, and this area is also currently in progress. Overall, both results areas demonstrate a structured progression from development and capacity building to validation and user engagement, reinforcing the shift toward data-driven policy support.

## Slide 7
5
Contribution to Sustainable Development Goals
__________________________________________________________________________________________________________________
Budget expenditure
$248,942
17.18, 17.19
SDG
SDG Target
Advancing data integration, innovation, and capacity in Africa
Verification disbursement linked results for data harmonization and quality
$36,000
$223,479
$658,400
Transforming Health Financing in Africa through data
Developing Capacity in CRVS innovative applications, E-CRVS shared Asset-ACSA
SP Contribution
2.3
16.6; 16.19 16.9;16.10
Innovative use of Earth Observations technology for the production and validation of crop statistic
Short-term training on Basic Agricultural Statistics
3.8

## Slide 8
ENVIRONMENTAL SUSTAINABILITY
DISABILITY INCLUSION
HUMAN RIGHTS
Cross-cutting issues
________________________________________________________________________________________________________
GENDER
6
Supported the STG 8 Technical Meeting on Migration, contributing to the validation of the 2026–2027 programme of work and the revised guidelines on migration statistics with emphasis on disaggregation by gender and age.
Strengthened GIS and Remote Sensing capacities in Eritrea to generate evidence for sustainable natural resource management and ecosystem protection.
Technical advisory support to strengthen the integration of gender-disaggregated data in NCD and agricultural surveys in future survey rounds in Kenya.
Technical advisory support for the verification of 2024 NCD and agricultural survey data in Kenya, with recommendations to enhance disability-inclusive and disaggregated data collection in future survey rounds.

## Slide 9
Scaling up the CRVS R-pipeline for efficiency, reproducibility, and transparency using open-source tools
Tailoring training content to different skill levels for enhanced learning outcomes and participant engagement.
Organize follow‑up technical coordination meetings with regional centers.
Continued and progressive capacity-building efforts to ensure effective adoption and sustainability of the R-based VS production approach.
Focused training modules allow deeper hands-on learning and better mastery of skills
Regional Centres of Excellence are central to sustainability, harmonization, and scaling.
Implementation Challenges
Lessons
Solutions
Reflections
_________________________________________________________________________________________
7
Diverse participant proficiency in GIS and limited prior exposure to R programming affected the pace and effectiveness of training on GIS and vital statistics.
Insufficient regional capacity structures to support harmonized and scalable implementation- in ESTELLA
Notes: This slide presents a summary of the key challenges encountered, the lessons learned from implementation, and the corrective and forward-looking solutions being put in place.
Starting with the challenges, one of the most significant constraints is the limited formalized data sharing between civil registration offices and national statistical offices. This lack of structured data exchange limits the ability to ensure consistency, interoperability, and timely integration of vital statistics into national systems. In addition, we continue to face infrastructure-related constraints. Limited internet bandwidth remains a major bottleneck, restricting reliable access to satellite imagery and essential geospatial services. This affects not only data acquisition but also the efficiency of workflows that depend on cloud-based or remotely hosted services.
Furthermore, limited data availability has posed challenges in fully verifying figures used in NADABAS outputs. This has implications for data quality assurance, validation processes, and ultimately the credibility and usability of the generated statistics. From these challenges, several important lessons have been drawn. First, effective data sharing must always be anchored in clear legal and institutional frameworks that safeguard confidentiality, privacy, and data protection. Without this foundation, sustainable data exchange cannot be achieved. Second, we learned that robust digital infrastructure is a prerequisite for modern statistical and geospatial systems. However, infrastructure alone is not sufficient—capacity building must go hand in hand with investments in systems and technology to ensure that institutions can effectively use and maintain these solutions. Third, timely, consistent, and complete access to data is essential. Without it, verification processes are weakened, and the reliability of outputs such as those from NADABAS is compromised. This highlights the importance of strengthening coordination and data governance mechanisms.
In response to these challenges and lessons, several targeted solutions are being implemented. We are developing interoperable systems designed to enable civil registration users to access anonymized data for analytical purposes. This approach ensures both usability and compliance with data protection requirements. We are also adopting more resilient and flexible data workflows. These combine local data storage with selectively synchronized cloud services, allowing us to mitigate the effects of limited connectivity while still enabling efficient data processing and sharing. In parallel, we are strengthening coordination with data providers by establishing clear data-sharing timelines and engaging stakeholders early in the process. This proactive approach is expected to improve data availability, reduce delays, and enhance the overall reliability of statistical production processes. In conclusion, these combined efforts are aimed at addressing structural bottlenecks, improving data governance, and ensuring that NADABAS outputs and geospatial analytics are more accurate, timely, and sustainable in the long term.

## Slide 10
8
New evidence for analysis
_________________________________________________________________________________________
1. Regional Harmonization and Interoperability
Through STG-12, ACS provided technical advisory support to countries and RECs on the implementation of international statistical classifications.
ACS facilitated High-level meeting for the adoption of the African Revenue Classification
40 experts from African NSOs trained for the adoption of ISIC, Rev 5, CPC, Rev. 3, COFOG, and EBOPS
2. Climate, Environment, and Sustainable Development Statistics
In partnership with FAO, strengthened capacities in the use of Earth Observation data for agricultural statistics and crop monitoring.
Built the capacity of young African fellows in agricultural statistics and data innovation to support climate and sustainable development reporting.
Developed a Water Statistics Block framework to strengthen water data systems in support of SDG 6 monitoring and promoting harmonized transboundary water statistics and governance across Africa.