# UNITED NATIONS ECONOMIC COMMISSION FOR AFRICA

## Weekly Division Update

Division/Section: 	African Centre for Statistics

Reporting Period:  	 01-08, March 2026

Submitted by: 		Samuel Kobina Annim, Director, African Centre for Statistics

Date Submitted:               	09 March 2026

| KPI Area | Target / Milestone | Progress This Week | Status (🟢/🟡/🔴) | Remarks |
| --- | --- | --- | --- | --- |
| IoA 1.1 (i) Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics (cumulative) (PPB 2026) Baseline (end of 2025): 46 Annual target (2026): 1 Cumulative target (47) = Baseline (46) + annual target (1) |  | No update |  |  |
| IoA (i) Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) PPB 2026 Baseline (end of 2025): 11 Annual target (2026): 14 Cumulative target (14) = Baseline (11) + annual target (3) |  | Burundi: Professional training on ArcGIS | 🟢 | Completed |
|  |  | Mali: Organizing a knowledge sharing Webinar for sustainable funding and return on investment of geospatial information. | 🟡 | Ongoing: Identification of the speakers |
|  |  | Eritrea: Capacity-building training on statistical and geospatial insights | 🟢 | Completed |
| IoA 1: number of members of ECA adopting innovative technology applications in civil registration and vital statistics systems (cumulative)) Baseline (end of 2025): 3 Target (2026): 3 Cumulative: 6 |  | National Capacity Building of the Republic of Rwanda on Communication and Messaging of Vital Statistics | 🟢 | East African Community |
| Draft: (i) Number of statistical products developed for use in policy formulation, monitoring and dissemination (cumulative) -non-PPB (2026) Baseline (end of 2025): 2 Annual target (2026): 4 Cumulative target (4) = Baseline (2) + Annual target (2) |  | No update |  |  |

### 2. Major Initiatives & Projects in previous week)

| Initiative / Project | Key Milestone This Week | Next Steps | Lead Officer |
| --- | --- | --- | --- |
| Eastern Africa Regional Statistics Program-for-Results | E-mail reminded sent to the EAC for potential DLI verification | Q2 Verification plan- draft | Joseph |
| Digital Censuses | Weekly meetings with Comoros and Madagascar on developing the dashboard. |  | William Baakal |
| Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) project | Ghana: Regional Workshop for West African countries identification of participants; liaison with focal points; invitation letters, etc. | Raising Travel Requests Arranging on-site logistics | Andre Nonguierma |
|  | Kenya: National Alignment Workshop – Preparatory Activities: Identification of participants, liaison with focal points, invitations letters, etc | Design of standardized survey template and field protocol | Andre Nonguierma |
| Google project | - Google Data commons knowledge graph tested to establish the African Data Commons platform - Satellite-Based Water Storage & Quality Monitoring Concept note presented | - AI augmented statistical production capacity building concept note for MS developed - Identify two datasets to start working on the pipelines for data curation | Molla |
| Specialized Technical Group on Classification Training Workshop on classifications |  |  | Ali |
| Mid-term review of the National Strategy for the Development of Statistics of Seychelles, | Collect additional information to support achievements at the mid-term implementation of the NSDS of Seychelles Draft the mid-term review report |  | Ilboudo Joseph, Leandre Ngogang, Angela Kiconco |
| Support to IGAD on the development of its second Regional Strategy for the Development of Statistics |  |  | Ilboudo Joseph, Leandre Ngogang, Angela Kiconco |
| Webinar series: Virtual Training on Forest Ecosystem Accounting – |  |  | David |

3. Missions

| Team Member(s) | Destination | Dates | Objective | Key Outcomes | Funding Source (RB / RPTC / XB) |
| --- | --- | --- | --- | --- | --- |
| Pamela Kakande Nabukhonzo | Kigali, Rwanda | 2 to 6 March 2026 | National Capacity Building of the Republic of Rwanda on Communication and Messaging of Vital Statistics | Disseminating and communicating vital statistics to different stakeholders | East African Community |
| Ayenika GODHEART MBIYDZENYUY And Peter NJAGI | Asmara, Eritrea | Feb 2- 27, 2026 | To conduct a comprehensive four-week capacity building program for technical staff at the Ministry of Lands, Water, and the Environment (MLWE), | - Strengthen staff understanding and practical abilities in using GIS and RS technologies to address these issues through intensive hands-on practice and real-world applications. - Enabled staff to apply these tools more effectively in their daily work, support assessment studies and research, enhance the implementation of various programs and projects, and improve the Ministry's overall Geospatial Information Management Systems (GIIMS). | RPTC |

### 4. Workshops / Conferences Conducted

| Title | Date / Venue | Objective | Outcome / Follow-up |
| --- | --- | --- | --- |

### 5. Analytical Work (Ongoing or Completed)

| Topic | Status | Strategic Relevance | Expected Output Date |
| --- | --- | --- | --- |
| Daily Statistical facts and figures | On going | - Supports the modernization of statistical dissemination and enhances visibility of African data within the ECA | Ongoing |
| Analytical work on African Statistical Yearbook - ASYB | On going | - Contributes to evidence-based policymaking through comprehensive analysis and harmonized continental statistics | March 2026 |
| Informal cross border trade | On going | - Enhances understanding of regional trade dynamics and supports AfCFTA monitoring and regional integration. | June 2027 |
| Development of Compendium for Disaster-related Statistics | Ongoing | - Updating and refining the compendium with the hazard list - Harmonizes the indicators and provides a standardized framework for monitoring, reporting, and managing disaster risks across sectors | March 2026 |
| CRVS Applied Research and Training | Ongoing | - Identifying barriers to universal vital events registration | December 2026 |
| AfCIOT | Ongoing | - Data preparation for the integration of four additional countries: Kenya, Mauritania, Niger and Uganda - Preparation of the work plan for 2026 - Updating trade data for AfCIOT | February 2026 |
| Monitoring Water Resources of Africa | - Monitoring water resources in Africa is ongoing. - A time-series analysis of Lake Chad's extent was conducted using Google Earth Engine. - A draft technical report is generated | - Time series analysis of water bodies is vital to show long-term trends and seasonal patterns in water resources, enabling policymakers and managers to understand changes over time. It informs decision-making across environmental, socio-economic, and geopolitical dimensions, such as resource allocation, environmental protection strategies, and community health planning. | Ongoing |
| Map Production, Spatial Analysis and Printing | Map Production and Clearance: - Health Facilities Map in Addis Ababa - Food Import Dependence Ratio (%) - Digital maps of census enumeration areas | - Strengthening Evidence-Based Policy and Decision-Making - Support ECA policy research work - Effective communication of complex information to policymakers, decision-makers, and the public. | Ongoing |
| ECA Web-Based Rapid Mapping tool | Ongoing – Draft stage | - Strengthens evidence-based decision-making, timeliness, and visibility of development interventions across member States | March 31, 2026 |
| Preparation of the end or programme narrative and financial reports of the EU grant to ECA. | Ongoing. Submitted to PRMS for review | - Donor accountability and dissemination of lessons learned and knowledge management | March31, 2026 |
| Data situation analysis platform for ECAStats | Deployed for use and integrated | - To provide objective assessment of data availability, recency and completeness by topics, outputs, and indicators | March 31 2026 |
| ECAStats enhancement | Under testing | - Enhancement of data presentations to users: Currently developing data story page | February 2026 |
| Development of over 60 Geospatial Training Technical Manuals on Land, Water and the Environment | On-Going | - Second Capacity Development Workshop on “Spatial Insights: Empowering Decision-Making and Transforming Knowledge into Action with Geospatial Intelligence.” 2 to 27 February 2025, Asmara, Eritrea | February 2026 |
| Land Statistics in Africa: The Value Proposition for Producing and Disseminating Development Indicator | On going | - Support to the ACS Value Proposition of the Africa Beyond Numbers Series | March 2026 |

### 6. Flagship Publications / Reports

| Title | Type | Status | Expected Launch / Submission |
| --- | --- | --- | --- |
| The 2026 Economic Report for Africa ERA) – Chap 4, ( Data – The new oil fueling frontier technologies | Flagship Report | The report updated with addressing comments from editors, acronyms and abbreviation list, and acknowledgement section and now shared with MFGD and TICID for further review and subsequent publication | March 31 2026 |

### 7. Grants & RPTC progress

| Title of project | Type (Grant/ DA/ RPTC) | % Of resource utilization | Expiry date |
| --- | --- | --- | --- |
| DA 15 Project: 2326D - Quantifying South-South cooperation to mobilize funds for the Sustainable Development Goals | DA | 68.8% | June 30, 2026 |
| AfDB Grant - Capacity Building for Gender Statistics and Monitoring Systems (CB-GenSMS) Grant # S1-32HDM-000226 | XB | 94.4% | 31 December 2025 (Expired – NCE requested Dec 2025) |
| Bloomberg Grant (1) - To improve collection of birth and death data systems in Africa Grant # S1-32HDM-000247 | XB | 84.6% | 31 March 2027 |
| EAC - Eastern Africa Regional Statistics Program-for-Results (EARSP-for-R) Grant # S1-32HDM-000254 | XB | 72.4% | June 2027 |
| UNPDF - Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) Grant # S1-32HDM-000274 | XB | 4.4% | 30 September 2028 |
| Bloomberg Grant (2)- Developing Africa E-CRVS Shared Asset for Improvement of Digitalization of CRVS System in Africa Grant # S1-32HDM-000277 | XB | 29.4% | 30 June 2027 |
| UNFIP - Advancing data integration, innovation, and capacity in Africa (Africa Google Data Commons) Grant # S1-32HDM-000280 | XB | 20.2% | 30 June 2027 |
| FAO - Short-term training on basic agricultural statistics and statistical data processing and presentation Grant # S1-32HDM-000285 | XB | 0% | 30 June 2026 |

### 8. Key Challenges & Mitigation Measures

| Challenge | Implication | Proposed Solution / Action |
| --- | --- | --- |

9.  Member States Request

| Member State | Date Received | The Request Made | Is the request being considered? | Status Update | Additional Remarks |
| --- | --- | --- | --- | --- | --- |

10. Other Noteworthy Developments; Insert narrative bullet points on high-impact items, strategic engagements, resource mobilization updates, or inter-agency collaboration