## IoA
Performance Metrics
RA | Indicator | Indicator definition: Provide a detailed explanation of what this indicator represents and how it will be measured. | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 | [5 empty] | Overview of Achievement (please provide a brief description of the result being reported)
Indicator of Achievement
|  |  | Milestones | Means of Verification: Identify the data source, i.e. how the status reported will be confirmed. Name and link to supporting documents to confirm achievement of actual reported. | Status | Milestones | Means of Verification: Identify the data source, i.e. how the status reported will be confirmed. Name and link to supporting documents to confirm achievement of actual reported. | Status | Milestones | Means of Verification: Identify the data source, i.e. how the status reported will be confirmed. Name and link to supporting documents to confirm achievement of actual reported. | Status | Milestones | Baseline | Target (2026) | Actual | Status | Means of Verification: Identify the data source, i.e. how the status reported will be confirmed. Name and link to supporting documents to confirm achievement of actual reported.
RA (1): members of ECA produce and disseminate comparable economic statistics Programme performance in 2024 and target for 2026 | Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics (cumulative) (PPB 2026) | The 2008 System of National Accounts (SNA 2008) and its extensions provide comprehensive guidelines for the measurement of economic activities, aiming for consistency and comparability accross countries. It provides international standards for measuring economic activity, focusing on GDP calculation, sectoral accounts, and capital formation. It includes frameworks for external sector accounts, environmental and household production accounting, and data reconciliation. Extensions also integrate natural resource accounting, wealth distribution, and align with Sustainable Development Goals (SDGs) for sustainable growth. The IoA measures the number of ECA memeber states advanced in adopting and applying the 11 recommended standards and methodologies (regularly updating the base year and the classifications). | Workshop on the new System of 2025 National Accounts and the new Balance of Payments Manual- BPM7, with a focus on the challenges faced by countries that have not yet transitioned to SNA 2008 | https://unitednations.sharepoint.com/:w:/s/ECA-SD-ACS/IQCPF6qd6AEqS5Ne4snVYrLTAUNps73wvw_hBKUb12qsmCA?e=W1mbPn |  | A country, that was not previously using SNA 2008, has produced a new series in accordance with SNA 2008. | https://unitednations.sharepoint.com/:f:/s/ECA-SD-ACS/IgDxTv4NxyzISozJZY9jb225AfaZXUzf72iyLoZYkOGHiHU?e=3T6NRa |  | Validation of the results for the new 2008 series for at least one country. | Meeting report; Validation report |  | A country, that was not previously using SNA 2008, has published a new series in accordance with SNA 2008 | 46 | 1 | 0 |  | ∞Official national accounts publications or reports aligned with SNA 2008 ∞Release of revised GDP series or related aggregates reflecting SNA 2008 methodology ∞Metadata documentation outlining methodological changes and compliance with SNA 2008 ∞Official communication or press release from the national statistical office announcing adoption ∞Data published on official platforms (e.g., NSO website or national data portals)
RA (2): progress towards integrated statistical and geospatial information frameworks Programme performance in 2024 and target for 2026 | Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) (PPB 2026) | The indicators support operationalization of the United Nations Integrated Geospatial Information Framework (UN-IGIF) in Africa by fostering country-specific action plans, sub-regional capacity-building workshops, and alignment with national development priorities. Progress will be measured by the number of member States applying at least one of the UN-IGIF's nine strategic pathways: (1) Governance and Institutions; (2) Policy and Legal; (3) Financial; (4) Data; (5) Innovation; (6) Standards; (7) Partnerships; (8) Capacity and Education; and (9) Communication and Engagement. | Capacity-building training on statistical and geospatial insights. | https://unitednations.sharepoint.com/:f:/s/ECA-SD-ACS/IgDfVcxYdtLYTb9cWP0TaP9wAUE8LixVKyS1TY90nBYAIoI?e=BZz1rf |  | Domesticated Action Plan for an Integrated Geospatial Information Framework (UN-IGIF) drafted | https://unitednations.sharepoint.com/:w:/s/ECA-SD-ACS/IQCsaYIsY9dHQYW0kzy9eJOuAXA3QNUvkb_Z1HpfIdTeHoM?e=JhmAKF |  | Priority Strategic Pathways Such as:( Governance, Data, Standards, Capacity) assessed | Means of Verifications: implementation roadmap on IGIF |  | UN‑IGIF Country-Level Action Plan developed and endorsed for Verifications | 21 | 3 | 1 | 1 | ∞Endorsed UN-IGIF Country-Level Action Plan document ∞Government approval or endorsement letter/minutes from relevant authority ∞Stakeholder validation workshop reports and attendance records ∞Final assessment/baseline reports informing the Action Plan ∞Published or accessible version of the Action Plan (e.g., website or repository) ∞Correspondence or formal communication confirming adoption and use for implementation
RA (3): improved civil registration and vital statistics systems | Number of members of ECA adopting innovative technology applications in civil registration and vital statistics systems (cumulative) (PPB 2026) | This indicator measures the cumulative number of ECA member States that have introduced and are applying innovative digital or data-driven technologies (e.g., R-based data pipelines, automation tools, interoperability solutions, or digital registration platforms) to improve the functioning of their CRVS systems, as a result of ECA-supported interventions, including trainings and technical assistance. What counts as “adoption” A country is counted when it demonstrates practical use of the technology, such as: ☐ Deployment or integration of R-based pipelines or similar tools in CRVS processes ☐ Use of automated data processing, validation, or analysis workflows ☐ Application of digital tools in registration, reporting, or vital statistics production | CRVS R pipeline training | https://unitednations.sharepoint.com/:f:/s/ECA-SD-ACS/IgCXzk1KFh_dR5oESPQddjPMAQIx5jA1t00tcJGuU50eQK8?e=kbH3Mr |  | Validated statistical tables produced using R Pipeline | https://unitednations.sharepoint.com/:f:/s/ECA-SD-ACS/IgDobK5ghbRqSYgIq2hCsxhlAQfLqoAKikz9ZjLAh3taORw?e=Y8kRx2 |  | Draft vital statistics report | Means of Verifications: ☐ Copies of R pipeline scripts, exercises, and training materials shared ☐ Training report (Agenda, Modules and Summary of Sessions) |  | CRVS validated reports | 0 | 3 | 1 |  | Rwanda has produced 2025 statistical report ∞Deployment records of the CRVS R application in member States ∞System access logs and usage statistics demonstrating active use ∞Official communication or confirmation from national authorities on adoption ∞Training reports and participant records on CRVS R application implementation ∞National reports or documentation referencing the use of CRVS R for civil registration and vital statistics ∞Outputs generated from the CRVS R application (e.g., vital statistics reports, automated tables, or dashboards) | ECA provided technical support and advisory services for the production of the 2025 Vital Statistics Report in Rwanda, strengthening national capacity in the management and dissemination of civil registration and vital statistics. Twenty-two government officials were trained in data processing using programming languages, and the CRVS R pipeline was adapted to integrate 2025 administrative records on births, deaths, and marriages. The support improved the quality and content of statistical outputs and enhanced the country's capacity to communicate vital statistics through innovative messaging approaches. The initiative was implemented in partnership with the East African Community (EAC), Vital Strategies, and Bloomberg Philanthropies.
RA (4): Strengthened statistical product innovations for enhanced policy linkages (Non PPB) | Number of statistical products developed for use in policy formulation, monitoring and dissemination (cumulative) | The indicator measures the number of statistical products developed by ACS: This indicator measures the number of statistical products developed and operationalized within the planinng period to support policy formulation, monitoring, and dissemination. These include analytical reports, policy briefs, dashboards, geospatial outputs, and interactive, integrated statistical portals that facilitate data access and use for decision-making. Products are counted if they: (i) align with policy priorities or national frameworks; (ii) are accessible to intended users; and (iii) demonstrate evidence of use. Evidence is established through user engagement survey reports, usage analytics (e.g., portal traffic and downloads), user engaement surverys, citations in policy documents, or stakeholder feedback | Interactive integrated statistical portal developed | https://unitednations.sharepoint.com/:f:/s/ECA-SD-ACS/IgBC2RBAca7oRK7yQ2acaKBFAY3kayWWX52kQzrs9_ZZf70?e=XmXibn |  | Feedback gathering survey launched | Means of verificaitons: Web links to published source, 2. User guides for portals, 3. Brochures and flyers |  | Mobile version of the portal developed | Means of verificaitons: Web links to published source, 2. User guides for portals, 3. Brochures and flyers |  | User engagement survey reports for policy use | 2 | 2 | 0 |  | ∞Published statistical products (e.g., reports, policy briefs, dashboards, geospatial outputs, and integrated statistical portals) ∞Repository or inventory of developed products maintained in ecastats ∞Usage analytics (e.g., downloads, portal traffic, user access logs) ∞User engagement and satisfaction survey reports indicating use in policy processes
Note on R6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Akrem Abdusemed for action please
Note on R7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Akrem Abdusemed please revise and leave only the means of verification for the IoA. Please do not refer to milestones
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Akrem Abdusemed please update the statistical tables as well. The report meets the IoA metric, 1 country but not the milestone Reply: Revised with tables from Namibia and Rwanda
Note on R8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Akrem Abdusemed please ask Prudence to provide a brief description of the achievement in Rwanda, articulating ECA contribution to the result. Reply: Brief description included
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Akrem Abdusemed please provide IoA definition for us to assess if milestones are logically linked to its achievement Reply: Revised, pending Molla’s approval

## Deliverables
PART II: DELIVERABLES REPORTING (as per PPB 2026) The status of ALL deliverables at Q1 should be duly reported. All columns MUST be completed. If you include non-PPB Deliverables, please indicate clearly “non-PPB”.
S/N | Deliverable | Approved Target (as indicated in PPB) | Actual | Status (Not started, in-progress, Completed, Delayed, Postponed, Terminated,) | Completion/Expected Completion month/Year | Budget (RB, RPTC, DA, XB) | Evidence (Please provide a link to supporting documentation) | Detailed Description (What, who, why, how) | Finacially Impacted (Please briefly describe impact non-delivery of the deliverable will have on member States)
A. | Facilitation of the intergovernmental process and expert bodies
Parliamentary documentation
| Statistical capacity development, to the Statistical Commission for Africa | 1 | 0 | In-progress | 2026-07-15 | RB, RPTC |  | The report will assess progress made by African countries in modernizing their statistical systems, strengthening institutional and human capacities, and enhancing data production and dissemination. It will highlight the adoption of innovative data sources and emerging technologies, including artificial intelligence (AI), geospatial information, big data, and digital data collection tools, to improve the timeliness, quality, and relevance of official statistics. The report will also identify key challenges, emerging opportunities, and recommendations for accelerating statistical transformation across the continent.
| Progress in population and housing censuses, to the Statistical Commission for Africa | 1 | 0 | In-progress | 2026-07-15 | RB, RPTC |  | The document aims to inform discussions on the status of the 20230 census implementation across the continent, highlight emerging challenges and good practices, and provide recommendations to strengthen census planning, execution, data dissemination, and utilization. It will serve as a basis for deliberations among representatives of National Statistical Offices (NSOs), Regional Economic Communities (RECs), policymakers, and development partners, with a view to advancing the production and use of quality population and housing census data in Africa.
| State of a gender perspective and social development statistics, to the Statistical Commission for Africa | 1 | 0 | In-progress | 2026-07-15 | RB, RPTC |  | The report will assess progress in mainstreaming gender across national statistical systems and strengthening the collection, analysis, dissemination, and use of gender and social development statistics across the continent. It will highlight advances in the production of gender-responsive data, identify persistent data gaps and challenges, and provide evidence to inform policymaking and support efforts toward gender equality and inclusive social development in Africa.
| Integration of geospatial and statistical data, to the Statistical Commission for Africa | 1 | 0 | In-progress | 2026-07-15 | RB, RPTC |  | The report will examine progress in the use of geospatial information to support official statistics and evidence-based policymaking across Africa. It will highlight opportunities and challenges in integrating geospatial and statistical data, advances in national spatial data infrastructures and geospatial frameworks, and practical applications of geospatial technologies in censuses and surveys. The report will also emphasize the importance of integrated geospatial and statistical information for monitoring development outcomes and advancing sustainable development across the continent.
| Implementation of the 2008 System of National Accounts, to the Statistical Commission for Africa | 1 | 0 | In-progress | 2026-07-15 | RB, RPTC |  | The report will review progress made by African countries in implementing the 2008 SNA, including GDP rebasing and the production of new national accounts data series. It will also highlight efforts to strengthen the capacity of national accounts and balance of payments compilers to plan and manage the transition to BPM7 and the 2025 SNA. In addition, the report will showcase the use of African Continental Input-Output Tables (AfCIOT) and Trade in Value Added (TiVA) outputs to support evidence-based economic analysis and policy formulation across the continent.
| Implementation of civil registration and vital statistics, to the Conference of African Ministers Responsible for Civil Registration | 1 | 0 | In-progress | 2026-07-15 | RB, RPTC |  | The assessment will provide an overview of progress made in strengthening CRVS systems, with particular attention to the adoption of innovative technologies and analytical tools, such as R, to enhance the production and dissemination of timely and high-quality vital statistics. It will further explore how research and innovation are contributing to improved registration practices, data quality, and the use of CRVS data for evidence-based policy formulation and socio-economic development in Africa.
| Geospatial information management, to the Regional Committee of United Nations Global Geospatial Information Management for Africa at its tenth, eleventh and twelfth meetings | 1 | 0 | In-progress | 2026-07-15 | RB, RPTC |  | The report will provide updates on efforts by member States to strengthen national geospatial information systems, including the development and implementation of national action plans and frameworks aligned with the United Nations Integrated Geospatial Information Framework (UN-IGIF). It will highlight achievements, challenges, and lessons learned in advancing geospatial information management and promoting the use of geospatial data for sustainable development and evidence-based decision-making across the continent.
Substantive services for meetings
| Statistical Commission for Africa | 1 | 0 | In-progress | 2026-10-15 | RB, RPTC |  | The 10th Session of the Statistical Commission for Africa (StatCom-Africa) will be held during the last week of October 2026 at the United Nations Conference Centre (UNCC) in Addis Ababa. The conference serves as the continent’s premier forum for reviewing progress on the implementation of statistical policies, recommendations, and resolutions adopted in 2024, and for considering new resolutions to strengthen Africa’s statistical systems. The session will bring together representatives of National Statistical Offices (NSOs), Regional Economic Communities (RECs), Specialized Technical Committees (STCs), line ministries, and development partners. Preparatory activities are currently underway, including the development of the concept note, provisional programme of work, draft conference documentation, invitation letters, and media and communication materials to support the successful organization of the session. | ACS has not secured RPTC funding support for the organization of the StatCom-Africa and UN-GGIM Africa sessions in 2026. Given the limited Regular Budget (RB) resources available, ACS may not be able to fully cover the costs associated with convening these sessions. This funding gap could affect the scale of participation, limit technical support and related preparatory activities, and potentially reduce the overall impact and effectiveness of the sessions.
| Conference of African Ministers Responsible for Civil Registration | 1 | 0 | Not started | 2026-12-15 | RB, RPTC |  | Expert group meetings and technical forums to advance discussions on the application of innovative technologies and data-driven approaches in Civil Registration and Vital Statistics (CRVS) systems.
| Regional Committee of United Nations Global Geospatial Information Management for Africa | 12 | 0 | In-progress | 2026-10-15 | RB, RPTC |  | The Commitee Meeting a regional body that promotes the development, coordination, and use of geospatial information in Africa to support sustainable development, improve decision-making, and strengthen the integration of geospatial and statistical data across member States. | ACS has not secured RPTC funding support for the organization of the StatCom-Africa and UN-GGIM Africa sessions in 2026. Given the limited Regular Budget (RB) resources available, ACS may not be able to fully cover the costs associated with convening these sessions. This funding gap could affect the scale of participation, limit technical support and related preparatory activities, and potentially reduce the overall impact and effectiveness of the sessions.
| Advisory Expert Group on National Accounts | 1 | 0 | In-progress | 2026-11-01 | RB |  | The Advisory Expert Group on National Accounts, will be held in the next quarters. In collaboration with the African Development Bank (AfDB), the World Bank, and the International Monetary Fund (IMF). The meeting on the implementation of the 2008 System of National Accounts (2008 SNA), the transition to the 2025 SNA and the latest Balance of Payments Manual, as well as emerging developments in debt statistics will be dscussed. .
B. | Generation and transfer of knowledge
Field and Technical Cooperation Projects
| On sectoral statistics, including agricultural, health, energy and employment statistics | 2 | 0 | In-progress | 2026-12-01 | RB, RPTC, XB, DA |  | Support to sectoral statistics remains ongoing across agriculture, health (NCD), tourism, migration, and price statistics. Through its Extra-Budgetary (XB), Development Account (DA), and Regular Programme of Technical Cooperation (RPTC) initiatives, ACS continues to provide technical assistance and advisory services to National Statistical Offices (NSOs) on data verification, quality assurance, and harmonization of sectoral statistics. Current activities include support for the validation and integration of agricultural, price, tourism, and geospatial data, as well as advisory assistance to member States in strengthening migration statistics and reporting under various Sustainable Development Goal (SDG) indicators.
| On the data warehouse | 1 | 0 | In-progress | 2026-12-01 | RB, RPTC, XB |  | Work on ECA-STAT, the Commission’s data warehouse, is ongoing to ensure the regular updating and dissemination of statistical data and indicators. Efforts are focused on expanding data coverage through the integration of new datasets and indicators to support monitoring of the Sustainable Development Goals (SDGs) and Agenda 2063. In addition, new initiatives, including Africa’s Health Financing Gaps and Investment Portal, are being developed to strengthen data accessibility, enhance evidence-based policymaking, and support development planning across the continent.
| On the development of supply-use tables, intraregional input-output tables and trade-in-value-added model | 1 | 0 | In-progress | 2026-08-01 | RB, RPTC, DA |  | The activity focuses on the development of Supply and Use Tables (SUTs), Intra-regional Input-Output Tables, and Trade in Value Added (TiVA) models to strengthen economic statistics and analytical capacity in Africa. ACS is leveraging the African Continental Input-Output Tables (AfCIOT) and TiVA indicators to enhance member States’ capacity in economic analysis, trade measurement, and evidence-based policymaking. Capacity development activities will be organized for member States to support the effective application of these tools and methodologies. To date, 28 African countries have been integrated into the tables, with the final product expected to be launched in the fourth quarter of 2026.
| On technical assistance on gross domestic product updating and rebasing in members of ECA | 1 | 0 | In-progress | 2026-08-01 | RB, RPTC |  | The activity focuses on providing technical assistance to member States of ECA on Gross Domestic Product (GDP) updating and rebasing, with the aim of strengthening the capacity of National Statistical Offices (NSOs) to compile accurate, timely, and internationally comparable national accounts statistics. The support includes improving data sources, methodologies, and compilation practices to ensure compliance with international statistical standards. This work is ongoing and continues to support countries in enhancing the quality and reliability of their macroeconomic statistics.
| On leading African countries to participate in the global updating and related testing of the 2008 System of National Accounts programme | 1 | 0 | In-progress | 2026-08-01 | RB, RPTC |  | The activity focuses on supporting African countries to actively participate in the global updating and testing programme of the 2008 System of National Accounts (2008 SNA). It provides technical advisory services to member States on Gross Domestic Product (GDP) rebasing and the improvement of national accounts compilation practices in line with evolving international statistical standards. The work aims to strengthen institutional and technical capacity of National Statistical Offices (NSOs) to produce high-quality, comparable macroeconomic statistics and to ensure effective engagement in the global SNA update process.
| On consumer price index data collection, compilation and application | 1 | 0 | In-progress | 2026-09-01 | RB, RPTC |  | The activity focuses on supporting member States in the collection, compilation, verification, and harmonization of Consumer Price Index (CPI) and price statistics to strengthen inflation measurement and price data systems across Africa. It aims to enhance the capacity of National Statistical Offices (NSOs) to produce accurate, timely, consistent, and internationally comparable price statistics in line with global standards. Technical advisory support on data verification and harmonization is currently underway in three member States, contributing to improved data quality and methodological consistency. The work also promotes the effective use of CPI and price statistics for economic analysis, policy formulation, and monitoring of price dynamics to inform evidence-based decision-making.
| African programme on a gender perspective and statistics | 1 | 0 | Not started | 2026-07-01 | RB, XB
| African programme on population and housing censuses | 1 | 0 | Not started | 2026-07-01 | RB, RPTC |  | The African Programme on Population and Housing Censuses is ongoing, with an annual workshop planned for August to further advance regional coordination and capacity development. As part of the initiative, ACS is providing technical advisory support to member States on innovative approaches to census data protection and confidentiality, with the aim of enabling secure and wider dissemination of high-quality census microdata. These efforts are strengthening national capacities to safeguard data privacy while enhancing the accessibility and usability of census data for evidence-based planning and policy formulation. An RPTC project is expected to boost the support in counties such as Madagascar and Comoros
| On mainstreaming and implementing the United Nations Integrated Geospatial Information Framework and harmonizing with the African Geodetic Reference Frame | 3 | 0 | In-progress | 2026-12-31 | RB, XB |  | The activity focuses on supporting member States in mainstreaming and implementing the United Nations Integrated Geospatial Information Framework (UN-IGIF) and ensuring its harmonization with the African Geodetic Reference Frame to strengthen national geospatial systems. It aims to enhance institutional and technical capacities for developing integrated, efficient, and sustainable geospatial information infrastructures that support national development priorities. Work is currently in progress in Mali and Eritrea, where efforts are advancing the development of nationally owned UN-IGIF implementation frameworks, further strengthening country ownership and practical application of geospatial information for planning, monitoring, and decision-making.
| Africa Programme on Accelerated Improvement of Civil Registration and Vital Statistics Systems | 1 | 0 | In-progress | 2026-06-01 | RB, XB |  | The Africa Programme on Accelerated Improvement of Civil Registration and Vital Statistics (APAI-CRVS) Systems is a continental initiative aimed at strengthening and modernizing CRVS systems across Africa. Within this framework, ECA is contributing to the acceleration of CRVS reforms through capacity building of experts in the use of statistical tools such as R, enabling the production of high-quality and timely vital statistics reports to support evidence-based policy analysis and decision-making. In addition, the development of the APAI-CRVS website is an ongoing deliverable, intended to enhance access to information, knowledge sharing, and coordination among stakeholders.
| On the development of a data science campus | 1 | 0 | In-progress | 2026-08-01 | RB |  | The activity focuses on runnning Data Science Campus as a joint initiative between the Economic Commission for Africa (ECA) and the National Institute of Statistics of Rwanda, with support from partners such as the UK Office for National Statistics (ONS-UK). The initiative aims to strengthen data and statistical capacity across member States through targeted training, knowledge exchange, and the application of modern data science methods. Various capacity-building programmes in data analytics, statistical production, and innovative data sources will be delivered to enhance the skills of national experts and support evidence-based decision-making.
| On support for African countries in the implementation of the 2030 Agenda and Agenda 2063 | 1 | 0 | Not started | 2026-10-01 | RB, XB
| Fellowship programme for young African scholars to build their capacity in data and statistics | 1 | 0 | In-progress | 2026-05-01 | XB |  | The Fellowship Programme for young African scholars is aimed at strengthening the next generation of statistical professionals by building their capacity in data and statistics.
| On the performance data management dashboard | 1 | 0 | In-progress | 2026-08-01 | RB, RPTC, XB |  | The activity focuses on the development and strengthening of the performance data management dashboard to enhance monitoring, analysis, and reporting of statistical and performance indicators. It includes ongoing system improvements, resolution of technical issues, and deployment support to ensure effective functionality and usability.
| On census and survey data tools and dissemination | 2 | 0 | In-progress | 2026-09-01 | RB, XB |  | The activity focuses on strengthening census and survey data tools and enhancing data dissemination systems to improve the accessibility, usability, and quality of official statistics.
Seminars, workshops, and training events
| Workshop on a statistical data exchange system for national statistical offices | 2 | 0 | Not started | 2026-08-01 | RB |  | The workshop aim to familiarize participants with the Statistical Data and Metadata Exchange (SDMX) standard and the Open SDG dissemination platform, emphasizing their role in SDG indicator exchange and dissemination. The overarching goal is to strengthen member states' capacities in collecting, managing, and disseminating SDG data, ensuring better interoperability with international databases. This initiative aims to centralize SDG data, enhance transparency in indicator dissemination, and improve overall data management. | Following the conclusion of support from Eurostat, the sustainability of this initiative is affected by limited resources, which may slow down further system development, reduce technical support to countries, and hinder the full institutionalization of modern data exchange standards.
| Training events on statistical leadership for heads and senior experts of national statistical offices and line ministries responsible for the production of statistics | 2 | 0 | Not started | 2026-10-01 | XB |  | The Statistical Leadership Training was originally designed to strengthen the leadership, management, and decision-making capacities of National Statistical Office (NSO) staff in the governance and coordination of National Statistical Systems. | The conclusion of support from the UK Office for National Statistics (ONS-UK) has resulted in a financial gap that constrains the full implementation of the programme and may affect its continuity, scale, and regional coverage.
| Workshop on modernizing statistical systems in Africa for the leaders and managers of national statistical offices | 2 | 0 | Not started | 2026-06-01 | RB, RPTC |  | The Workshop on Modernizing Statistical Systems in Africa aims to equip leaders and managers of National Statistical Offices (NSOs) with the knowledge and skills needed to drive the modernization of National Statistical Systems through digital transformation, innovation, improved data governance, and the adoption of international statistical standards and best practices. | Following the conclusion of support from Eurostat, the sustainability of this initiative is affected by limited resources
| Workshop on population and housing censuses and progress on related population and housing censuses for experts and managers of national statistical offices and planning commissions | 2 | 0 | In-progress | 2026-07-01 | RB, XB |  | Workshop on population and housing censuses and progress on related population and housing censuses for experts and managers of national statistical offices and planning commissions. it is annual engagemen of NSOs and partners to measure the progress of the 2030 PHC | The is risk of limited finacial coverage. The non-delivery of this workshop would limit opportunities for senior managers to be exposed to modern approaches, tools, and best practices in statistical system modernization, potentially slowing the pace of digital transformation, weakening coordination of national statistical systems, and affecting the overall implementation of statistical modernization agendas across member States.
| Regional workshops on gender statistics for experts in national statistical offices and line ministries | 2 | 0 | In-progress | 2026-07-01 | RB, XB |  | The Regional Workshops on Gender Statistics bring together experts from National Statistical Offices and line ministries to strengthen the production, analysis, and use of gender statistics, promote the adoption of international standards and methodologies, and support the integration of gender perspectives into national statistical systems and development planning.
| Workshops on civil registration and vital statistics for experts of national ministries responsible for the production of civil registration and vital statistics data | 2 | 0 | In-progress | 2026-08-01 | RB, DA, RPTC |  | The Capacity-Building Workshops on Civil Registration and Vital Statistics (CRVS) are designed to strengthen the technical skills of experts from ministries and institutions responsible for the production of civil registration and vital statistics data. The workshops focus on training participants in the use of the CRVS R Pipeline, automated vital statistics report generation, the CRVS Assessment and Research Toolkit (CART), and the production of CRVS-based analytical reports and research to support evidence-based policymaking
| Training events on national accounts, environmental and economic statistics and accounting for national statistical offices and ministries of finance | 3 | 0 | Not started | 2026-10-01 | RB, DA, RPTC |  | The Training Events on National Accounts, Environmental-Economic Statistics, and Accounting are designed to strengthen the capacity of experts from National Statistical Offices and Ministries of Finance in the compilation and analysis of national accounts and related statistics. The training focuses on GDP rebasing methodologies, the implementation of the System of National Accounts (SNA), supply and use tables, environmental-economic accounting, and the production of high-quality economic statistics to support evidence-based policymaking and sustainable development.
| Regional seminars on the consumer price index, agricultural statistics and energy statistics | 2 | 1 | In-progress | 2026-10-01 | RB, RPTC |  | The Regional Seminars on Consumer Price Index (CPI) are primarily online capacity-building events aimed at strengthening the capacity of experts from National Statistical Offices while promoting the harmonization of CPI methodologies, concepts, and compilation practices across African countries. The seminars support the adoption of international standards to improve the comparability, quality, and consistency of inflation statistics in the region.
| Training workshop on geospatial knowledge infrastructure and fundamental geospatial datasets for monitoring the Sustainable Development Goals | 10 | 1 | In-progress | 2026-11-01 | RB, RPTC |  | The Training Workshop on Geospatial Knowledge Infrastructure, Fundamental Geospatial Datasets, and Geospatial Insights aims to strengthen the capacity of experts from National Mapping Agencies and related institutions in the development, management, and use of fundamental geospatial datasets and geospatial insights. The workshop supports the integration of geospatial and statistical information for SDG monitoring, evidence-based policymaking, and sustainable development planning.
| Workshop on the strategy for the integration of statistical and geospatial information for national mapping agencies and statistical offices | 5 | 0 | In-progress | 2026-10-01 | RB, RPTC |  | The Workshop on the Strategy for the Integration of Statistical and Geospatial Information aims to strengthen the capacity of National Mapping Agencies and National Statistical Offices to integrate statistical and geospatial data for improved decision-making. The workshop focuses on the use of Geographic Information Systems (GIS) in population and housing censuses, climate and environmental monitoring, and the implementation of national strategies aligned with the Global Statistical Geospatial Framework (GSGF).
| Training events on the development of national action plans on the United Nations Integrated Geospatial Information Framework for national mapping agencies | 5 | 2 | In-progress | 2026-10-01 | RB, RPTC |  | The Training Events on the Development of National Action Plans for the United Nations Integrated Geospatial Information Framework (UN-IGIF) aim to support National Mapping Agencies in formulating and domesticating action plans for the implementation of the UN-IGIF. The training focuses on strengthening institutional arrangements, governance, data infrastructure, capacity development, and partnerships to enhance the production, management, and use of geospatial information for sustainable development.
| Training events on geospatial knowledge infrastructure with innovative geospatial responses and solutions | 5 | 1 | In-progress | 2026-10-01 | RB, RPTC |  | The Training Events on Geospatial Knowledge Infrastructure aim to strengthen the capacity of National Mapping Agencies and National Statistical Offices in developing and applying integrated geospatial systems, with a focus on innovative geospatial responses and solutions
| Training events on big data and data science for the modernization of the production of economic statistics | 2 | 0 | Not started | 2026-11-01 | RB, RPTC |  | The Training Events on Big Data and Data Science aim to strengthen the capacity of National Statistical Offices and relevant institutions in the use of innovative data sources, analytics, and machine learning techniques to modernize the production of economic statistics. The training focuses on improving the timeliness, granularity, and quality of economic data through advanced data science methods and the integration of big data into official statistical production systems. | Limited funding in previous years has constrained the implementation of Training Events on Big Data and Data Science for the modernization of economic statistics, resulting in non-delivery of planned activities. This has slowed the adoption of advanced data science methods and alternative data sources in official statistics, reduced opportunities for capacity development in National Statistical Offices, and delayed efforts to improve the timeliness, granularity, and innovation of economic statistics production
| Advisory Expert Group on National Accounts meeting | 1 | 0 | Not started | 2026-07-01 | RB |  | The Advisory Expert Group on National Accounts (AGNA) meeting, in collaboration with STAFIC, AFRISTAT, and other partners, brings together experts from National Statistical Offices and regional and international organizations to provide technical guidance on national accounts compilation. The discussions focus on harmonizing methodologies, addressing emerging statistical challenges, and strengthening capacity in the implementation of the System of National Accounts, including GDP estimation and related economic statistics across countries.
| Technical workshop on environmental-economic accounting | 3 | 0 | Not started | 2026-09-01 | RB, DA, XB |  | The Technical Workshop on Environmental-Economic Accounting focuses on the application of the System of Environmental-Economic Accounting Central Framework (SEEA-CF) to strengthen the integration of environmental and economic statistics. The workshop builds the capacity of National Statistical Offices and relevant institutions in compiling environmental accounts, linking environmental data with economic indicators, and supporting evidence-based policymaking for sustainable development. | Limited funding in previous years led ACS to deliver the Technical Workshop on Environmental-Economic Accounting virtually rather than in full in-person format. This reduced hands-on training and peer learning, slowing capacity development and the integration of environmental-economic accounts into national statistical systems for policy use.
Publications
| Africa Sustainable Development Report | 1 | 0 | In-progress | 2026-12-01 | RB |  | The Africa Sustainable Development Report, in collaboration with UNDP and the African Union Commission (AUC), includes a dedicated chapter on data and statistics that highlights progress, gaps, and priorities for strengthening national statistical systems in Africa. The chapter emphasizes the critical role of quality, timely, and disaggregated data in tracking SDG implementation and supporting evidence-based policymaking across the continent.
| Africa Statistics Flash | 1 | 0 | In-progress | 2026-12-01 | RB |  | The Africa Statistics Flash, now referred to as “Daily Numbers,” is a regular statistical dissemination product that provides timely updates on key economic and social indicators for Africa. It is designed to enhance the accessibility and visibility of official statistics by delivering concise, up-to-date data to support evidence-based decision-making and public awareness.
Technical materials
| African regional geospatial databases, online services and geoportals | 1 | 0 | In-progress | 2026-12-01 | RB, RPTC |  | The African Regional Geospatial Databases, Online Services, and Geoportals initiative aims to strengthen access to and use of harmonized geospatial data across the continent. It focuses on developing and maintaining interoperable geospatial databases, expanding online services, and enhancing geoportals to support the integration of geospatial and statistical information for decision-making, planning, and monitoring of sustainable development initiatives.
| African atlas of spatial statistics | 1 | 0 | In-progress | 2026-08-01 | RB |  | The African Atlas of Spatial Statistics is a regional initiative aimed at compiling, harmonizing, and visualizing spatially disaggregated statistical data to support evidence-based policymaking and sustainable development.
| African Statistical Yearbook | 1 | 0 | In-progress | 2026-05-01 | RB |  | The African Statistical Yearbook 2025, which will be produced the United Nations Economic Commission for Africa, is an annual publication that compiles harmonized and comparable statistical data from African countries, covering key economic, social, and environmental indicators.
| Compendium of Intra-African and Related Foreign Trade Statistics | 1 | 0 | In-progress | 2026-09-01 | RB |  | The Compendium of Intra-African and Related Foreign Trade Statistics is a publication produced by the United Nations Economic Commission for Africa that provides harmonized and comparable data on trade flows between African countries and between Africa and the rest of the world. It compiles validated statistics on intra-African trade, exports, imports, and related trade indicators to support analysis of regional integration, trade policy formulation, and monitoring of initiatives such as the African Continental Free Trade Area (AfCFTA
| Census and survey results issues tracker, monitoring dashboard, communication, dissemination, and knowledge management toolkit | 4 | 0 | In-progress | 2026-10-01 | RB, RPTC, XB |  | The Census and Survey Results Issues Tracker, Monitoring Dashboard, Communication, Dissemination, and Knowledge Management Toolkit helps National Statistical Offices more easily track and resolve data issues, monitor census and survey results, and improve how official statistics are shared and communicated. It also supports better knowledge management and ensures that census and survey findings are timely, clear, and useful for decision-making
| Automated country data harvester | 1 | 0 | In-progress | 2026-10-01 | RB, RPTC, XB |  | The Automated Country Data Harvester is a digital tool designed to automatically collect, compile, and update statistical data from national and international sources for use by National Statistical Offices and regional organizations.
| Performance data management dashboard | 1 | 0 | In-progress | 2026-10-01 | RB, RPTC, XB |  | The Performance Data Management Dashboard is a digital tool that enables National Statistical Offices and partner institutions to track, visualize, and manage performance indicators in real time.
C. | Substantive Deliverables
Consultation, advice and advocacy
| technical advice on civil registration and vital statistics, on the 2025 planned population and housing censuses for members of ECA, on Sustainable Development Goal indicators and on developing integrated geospatial information frameworks at the national and regional levels. | 3 | 1 | In-progress | 2026-12-31 | RB, RPTC, XB |  | We will provide advisory and technical support to National Statistical Offices (NSOs) to strengthen Civil Registration and Vital Statistics (CRVS) systems, improve the tracking of Sustainable Development Goal (SDG) indicators, and support the integration of Geographic Information Systems (GIS) into census applications. This will help improve data quality, strengthen spatial analysis, and support more informed and evidence-based decision-making at both national and regional levels.
| Technical advice to members of ECA on matters related to digitalization, statistical management, economic statistics, survey and census and data science. | 5 | 0 | In-progress | 2026-12-01 | RB, RPTC, XB, DA |  | Technical advice will be provided to member States of the United Nations Economic Commission for Africa on digitalization of census applications, statistical management, economic statistics, surveys and censuses, and the application of data science to modernize official statistics for evidence-based policymaking.
| Technical advice to three members of ECA on geospatial-related matters. | 3 | 0 | In-progress | 2026-12-01 |  |  | Technical advice will be provided to three member States of the United Nations Economic Commission for Africa on geospatial integration challenges, including limited GIS capacity and weak linkage of geospatial and statistical data for climate and environmental monitoring, water resource management, and evidence-based decision-making.
Databases and substantive digital materials:
| ECA statistical data portal (ECAStats), providing data for members of ECA; geospatial databases (2), online applications, services and platforms (2); Africa GeoPortal. | 5 | 1 | In-progress | 2026-12-31 | RB, XB, RPTC |  | These are standard web-based applicatiosn with customized interface for geospatial information management. The web solutions also serve as a gateway to all our more “spatialized” web applications; organized and interactive for navigating information, e.g. by subject (category/theme) then sub-category/sub-theme in order to receive information about the topics and services that interest a user/visitor to the website.
D. | Communication deliverables
Outreach programmes, special events, and information materials
| African Statistics Day; annual Africa Symposium on Statistical Development; dissemination of information through outreach programmes and mobile applications. | 3 | 0 | Not started | 2026-10-26 | RB |  | These are regional statistical outreach and dissemination initiatives in Africa that promote the use and visibility of official statistics. They include African Statistics Day, the annual Africa Symposium on Statistical Development, and outreach programmes and mobile applications, all aimed at improving awareness, accessibility, and the use of data for evidence-based decision-making across the continent
External and media relations
N/A
Digital platforms and multi-media content
N/A
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Akrem Abdusemed please can you confirm that ACS has not completed a single delivery as at Q2? Reply: Confirmed
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Akrem Abdusemed please can you complete this column for all deliverables. Reply: Completed
Note on B62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Akrem Abdusemed I have included “approved target” in this section using the areas of work delineated or the countries mentioned i.e. in cel B64, there are 3 areas of work that the SP plans to provide technical advice on