# UNITED NATIONS ECONOMIC COMMISSION FOR AFRICA

## Weekly Division Update

Division/Section: 	African Centre for Statistics

Reporting Period: 	29 Dec 2025-4 January 2026

Submitted by: 		Samuel Kobina Annim, Director, African Centre for Statistics

Date Submitted:  		 January 2026

| KPI Area | Target / Milestone | Progress This Week | Status (🟢/🟡/🔴) | Remarks |
| --- | --- | --- | --- | --- |
| RA: Towards digital transformation and modernization of statistical systems IoA: Number of members of ECA that implemented the road map on digital transformation and modernized official statistics (cumulative) | Milestone: National Statistical System (NSS) maturity model assessment questionnaire validated Baseline (end of 2024): 13 Target (2025): 6 Cumulative Target: 19 | None |  |  |
| RA: Members of ECA produce and disseminate comparable economic statistics. IoA 1: Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics (cumulative) | Milestone: Eritrea publishes data according to 2008 SNA Baseline (end of 2024): 42 Target (2025): 2 Cumulative Target (Baseline + Annual Target): 44 | No update |  |  |
| RA: Progress towards integrated geospatial information frameworks IoA 1: Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) | Milestone: Mali, Mozambique and other countries continue to develop their geospatial knowledge infrastructure (in policies, data, capacities). Baseline (end of 2024): 8 Target (2025): 3 Cumulative: 11 | None |  |  |
| RA: Improved CRVS system performance IoA: Number of member states adopting innovative technology applications in CRVS systems. | Milestone: South Sudan and Burundi CRVS digital system operational Baseline (end of 2024: 0 Target (2025): 3 Cumulative: 3 | Preparations for the CRVS R-Pipeline training for Togo Selection of Research papers for the CRVS Forum |  |  |

### 2. Major Initiatives & Projects in previous week)

| Initiative / Project | Key Milestone This Week | Next Steps | Lead Officer |
| --- | --- | --- | --- |
| Eastern Africa Regional Statistics Program-for-Results | No update | Follow up for potential DLIs | Joseph |
| Digital Censuses | Assisting Lesotho National Bureau of Statistics with acquisition of tablets for the census | Ministry of Finance looking into the budget for procuring census tablets | William Molla |
| Migration of GIS: infrastructure to the cloud | No update |  | Peter Njagi Meron Kinfemichael Meazanesh Asres |
| Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) project | No update |  | Andre Nonguierma |
| UN-PDF call for proposals | No update | Review and incorporate comments | Eileen, Ayenika Godheart Andre Nonguierma |
| Google project | No update |  | Molla |
| Specialized Technical Group on Classification | None | - Draft Agenda and Concept Note for training on classifications - Meeting with UNSD and AU-STATAFRIC for training on classifications | Ali |

3. Missions

| Team Member(s) | Destination | Dates | Objective | Key Outcomes | Funding Source (RB / RPTC / XB) |
| --- | --- | --- | --- | --- | --- |
| None |  |  |  |  |  |

### 4. Workshops / Conferences Conducted

| Title | Date / Venue | Objective | Outcome / Follow-up |
| --- | --- | --- | --- |
| None |  |  |  |

### 5. Analytical Work (Ongoing or Completed)

| Topic | Status | Strategic Relevance | Expected Output Date |
| --- | --- | --- | --- |
| Daily Statistical facts and figures | On going | - Supports the modernization of statistical dissemination and enhances visibility of African data within the ECA | Ongoing |
| Developing Manuals and Guidelines on the Pseudonymization of GPS Coordination | Ongoing - draft stage Presentation of the concept to the African geospatial community to raise awareness and get their acceptance and support | - Strengthens data governance, confidentiality, and security standards in geospatial data collection and coordination | December 2025 |
| Analytical work on African Statistical Yearbook - ASYB | On going | - Contributes to evidence-based policymaking through comprehensive analysis and harmonized continental statistics | March 2026 |
| Informal cross border trade | On going | - Enhances understanding of regional trade dynamics and supports AfCFTA monitoring and regional integration. | June 2027 |
| 4th Eritrean Population and Health Survey | On-going | - Tabulation of data of the survey completed. - Preparation for the report writing workshop schedule for February 2026 (need for financial resources to secure ECA support) | December 2025 |
| Development of Compendium for Disaster-related Statistics | Ongoing | - Updating and refining the compendium with the hazard list - Harmonizes the indicators and provides a standardized framework for monitoring, reporting, and managing disaster risks across sectors | March 2026 |
| Inequality Assessments of Birth Registration using Census Data | Ongoing | - Identifying children being left behind in birth registration. | December 2025 |
| CRVS Applied Research and Training | Ongoing | - Identifying barriers to universal vital events registration | December 2026 |
| AfCIOT | Ongoing | - Data preparation for the integration of four additional countries: Kenya, Mauritania, Niger and Uganda | December 2025 |
| Geospatial approaches for impact assessment of mining operations on the hydrosphere | First draft completed on November 11, 2025 Under refinement based on the comments and feedback received. | - Geospatial analysis of mining impacts enables evidence-based prioritization of hotspot sites, guiding planning, interventions, and decision-making. - By comparing water quality and hydrosphere conditions before and after mining, this approach supports SDG 6 (safe drinking water, sanitation, and hygiene) through sustainable water resources management and ecosystem protection. - This monitoring helps safeguard communities and the environment, contributing to SDG 13 (Climate Action) and SDG 14 (Life Below Water) by integrating climate measures into mining strategies and preventing pollution of aquatic systems. | December 2025 |
| Monitoring Water Resources of Africa | Ongoing - Time series analysis of Lake Chad extent | - Monitoring water resources in Africa is ongoing. - Timeseries analysis of Lake Chad extent was conducted using Google Earth Engine - Time series analysis of water bodies is vital to show long-term trends and seasonal patterns in water resources, enabling policymakers and managers to understand changes over time. It informs decision-making across environmental, socio-economic, and geopolitical dimensions. | Ongoing |
| Map Production, Spatial Analysis and Printing | Ongoing | - Strengthening Evidence-Based Policy and Decision-Making | Ongoing |
| ECA Web-Based Rapid Mapping tool | Ongoing – Draft stage | - The tool will enable ECA staff and member-country experts to visualize spatial data without specialized GIS software or skills. Unlike other rapid mapping tools like Power BI or excel which lack the UN standardized basemap, this tool ensures UN standardized outputs. The app is designed for quick, professional map preparation, especially for presentations and reports. | January 31, 2026 |
| Literature review of publications and information sources for monitoring investment trends in Africa | On going | - provides an evidence-based foundation to identify, analyze, and monitor investment trends in Africa, informing policy decisions, programme design, and alignment with continental and global development agendas. | January 31, 2026 |
| Preparation of the end or programme narrative and financial reports of the EU grant to ECA. | On going | - Ensures accountability, transparency, and compliance with donor requirements while demonstrating results achieved and the effective use of resources. | January 31, 2026 |

### 6. Flagship Publications / Reports

| Title |  | Type | Status | Expected Launch / Submission |
| --- | --- | --- | --- | --- |
| 2024 Africa SDGs Progress Report: Is Africa on track to achieve the 2030 Goals? |  | Flagship Report | In progress | January 2026 |
| The 2026 Economic Report for Africa (ERA) – Chap 4, Data – The new oil fueling frontier technologies | Flagship Report | A data quality review of the ERA was conducted. Updated the chapter, taking into account the DES comments | Already submitted, and waiting for further comments to be considered |
| African Statistical Flash- for the Month of August |  | Flagship Report | In progress for Q4 | December |
| Preparation of ECA contributions to Africa Common positions - 57th UNSC |  | Report | In progress - Common position being drafted and country nomination to lead Africa’s position in the various sessions being identified. | January 2026 |
| Note of ACS for MFGD and other divisions on trade statistics |  | Short note | In progress Data compilation for trade-in service statistics for 2024 Draft note in preparation | 8 January 2026 |

### 7. Grants & RPTC progress

| Title of project | Type (Grant/ DA/ RPTC) | % Of resource utilization | Expiry date |
| --- | --- | --- | --- |
| - Support to Eritrea and South Sudan - Enhancing Statistical Capacity: Togo GDP Rebasing Project 2025 (Phase 1) IO-11605200 | RPTC | 98.9% | Dec 2025 |
| DA 14 Project: 2225A - Resilient and agile national statistical systems to meet post-COVID-19 data needs to recover better | DA | 98.1% | 31st December 2025 |
| DA 15 Project: 2326D - Quantifying South-South cooperation to mobilize funds for the Sustainable Development Goals | DA | 68.6% | June 30, 2026 |
| AfDB Grant - Capacity Building for Gender Statistics and Monitoring Systems (CB-GenSMS) Grant # S1-32HDM-000226 | XB | 96.4% | 31 December 2025 |
| Bloomberg Grant - To improve collection of birth and death data systems in Africa Grant # S1-32HDM-000247 | XB | 77.2% | 31 March 2027 |
| Eastern Africa Regional Statistics Program-for-Results (EARSP-for-R) Grant # S1-32HDM-000254 | XB | 113.5% | June 2027 |
| Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) Grant # S1-32HDM-000274 | XB | 0% | 30 September 2028 |
| Developing Africa E-CRVS Shared Asset for Improvement of Digitalization of CRVS System in Africa Grant # S1-32HDM-000277 | XB | 1.8% | 30 June 2027 |
| Africa Google Data Common Grant # | XB | 0% | 30 June 2027 |

### 8. Key Challenges & Mitigation Measures

| Challenge | Implication | Proposed Solution / Action |
| --- | --- | --- |
| None |  |  |

9.  Member States Request

| Member State | Date Received | The Request Made | Is the request being considered? | Status Update | Additional Remarks |
| --- | --- | --- | --- | --- | --- |
| None |  |  |  |  |  |

10. Other Noteworthy Developments; Insert narrative bullet points on high-impact items, strategic engagements, resource mobilization updates, or inter-agency collaboration

None