# UNITED NATIONS ECONOMIC COMMISSION FOR AFRICA

## Weekly Division Update

Division/Section: 	African Centre for Statistics

Reporting Period: 	26 January- 01 February 2026

Submitted by: 		Samuel Kobina Annim, Director, African Centre for Statistics

Date Submitted:              02nd February 2026

| KPI Area | Target / Milestone | Progress This Week | Status (🟢/🟡/🔴) | Remarks |
| --- | --- | --- | --- | --- |
| IoA 1.1 (i) Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics (cumulative) (PPB 2026) Baseline (end of 2025): 46 Annual target (2026): 1 Cumulative target (47) = Baseline (46) + annual target (1) |  |  |  |  |
| IoA (i) Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) PPB 2026 Baseline (end of 2025): 11 Annual target (2026): 14 Cumulative target (14) = Baseline (11) + annual target (3) |  | - Mali: Continued the preparatory activities for the National Forum on the United Nations Integrated Geospatial Information Framework (UN-IGIF) in Mali. - Eritrea: Preparation of the manuals and data, applications and the capacity development training on GIS and Remote Sensing. | 🟡 | The Mali Forum is schedule to take place on 9 –13 Fevrier 2026 The Eritrea training will kick-off on 2 February 2026 for four weeks. |
| IoA 1: number of members of ECA adopting innovative technology applications in civil registration and vital statistics systems (cumulative)) Baseline (end of 2025): 3 Target (2026): 3 Cumulative: 6 |  |  |  |  |
| Draft: (i) Number of ECA member States that have produced innovative statistical products for use in policy formulation, monitoring dissemination -non-PPB Baseline (end of 2025): 0 Annual target (2026): 8 Cumulative target (8) = Baseline (0) + Annual target (8) |  |  |  |  |

### 2. Major Initiatives & Projects in previous week)

| Initiative / Project | Key Milestone This Week | Next Steps | Lead Officer |
| --- | --- | --- | --- |
| Eastern Africa Regional Statistics Program-for-Results | Initial Finding Report reviewed by the EAC | Virtual Meeting with NISR and EAC scheduled for the 2ND week of February on the identified Verification protocols | Joseph |
| Digital Censuses | No update |  | William Molla |
| Migration of GIS: infrastructure to the cloud | Discussion with the United Nations International Computing Centre (UNICC) to evaluate their UNIQCloud, a state-of-the-art private cloud solution designed specifically for the UN system. | Undertake the benchmarking of UNICC proposal against the other solutions we have received (UNGC, Esri, Google, ICTSS, etc.). | Peter Njagi Meron Kinfemichael Meazanesh Asres |
| Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) project | - Planning and preparatory activities with the Ministry of Agriculture for the kick-off meeting of ESTELLA in Kenya: 10–12 February in Nairobi. - Engagement with regional partners for the holding of the inaugural regional coordination meeting. | - Organizing the meeting with participation of PRMS on behalf of ECA - Follow up with regional partners to agree on the date of the coordination meeting. | Andre Nonguierma |
| UN-PDF call for proposals | Project proposal and submitted | Awaiting the outcomes of the assessment from DPMO | Eileen, Ayenika Godheart Andre Nonguierma |
| Google project | No update |  | Molla |
| Specialized Technical Group on Classification Training Workshop on classifications | Participant countries are selected. Meeting for logistics arrangement | Invitation letters drafted and signed. Updated Agenda and Concept Notes | Ali |

3. Missions

| Team Member(s) | Destination | Dates | Objective | Key Outcomes | Funding Source (RB / RPTC / XB) |
| --- | --- | --- | --- | --- | --- |
| Lerato Makana | Asmara, Eritrea | 19 – 30 January, 2026 | Strengthen Eritrea National Statistics Office (NSO) in the compilation of GDP by production approach, and using NADABAS as a tool for the compilation process | Trained National Accounts compilers Deployment of NADABAS for Eritrea NSO | RPTC-Census |
| Andre Nonguierma | Nairobi, Kenya | 26-27 January 2026 | The objectives of the mission were to: - Support the Regional Centre for Mapping of Resources (RCMRD) deliberations on leadership transition and institutional strengthening aligned to the 2026–2030 Strategy. - Identify areas where UNECA can provide targeted technical assistance (governance, performance management, leadership development, recruitment processes). | The meeting: - Reviewed and confirmed onboarding of the new HR and Communications Managers. - Noted urgency of recruiting a new Corporate Services Director. - Discussed the Director General’s tenure, recommending a two-year extension (Nov 2026–Nov 2028. - Reviewed the HR Plan findings, leadership assessment limitations, governance gaps, and agreed on immediate, medium-term, and long-term action points. | No Cost to ECA: Borne by organizers Note on confidentiality requirement: This report summarizes internal committee deliberations and is shared on a need‑to‑know basis. |

### 4. Workshops / Conferences Conducted

| Title | Date / Venue | Objective | Outcome / Follow-up |
| --- | --- | --- | --- |

### 5. Analytical Work (Ongoing or Completed)

| Topic | Status | Strategic Relevance | Expected Output Date |
| --- | --- | --- | --- |
| Daily Statistical facts and figures | On going | - Supports the modernization of statistical dissemination and enhances visibility of African data within the ECA | Ongoing |
| Analytical work on African Statistical Yearbook - ASYB | On going | - Contributes to evidence-based policymaking through comprehensive analysis and harmonized continental statistics | March 2026 |
| Informal cross border trade | On going | - Enhances understanding of regional trade dynamics and supports AfCFTA monitoring and regional integration. | June 2027 |
| Development of Compendium for Disaster-related Statistics | Ongoing | - Updating and refining the compendium with the hazard list - Harmonizes the indicators and provides a standardized framework for monitoring, reporting, and managing disaster risks across sectors | March 2026 |
| CRVS Applied Research and Training | Ongoing | - Identifying barriers to universal vital events registration | December 2026 |
| AfCIOT | Ongoing | - Data preparation for the integration of four additional countries: Kenya, Mauritania, Niger and Uganda - Preparation of the work plan for 2026 | February 2026 |
| Monitoring Water Resources of Africa | Ongoing - Time series analysis of Lake Chad extent | - Monitoring water resources in Africa is ongoing. - Timeseries analysis of Lake Chad extent was conducted using Google Earth Engine - Time series analysis of water bodies is vital to show long-term trends and seasonal patterns in water resources, enabling policymakers and managers to understand changes over time. It informs decision-making across environmental, socio-economic, and geopolitical dimensions. | Ongoing |
| Map Production, Spatial Analysis and Printing | - Continuous activity: - Poverty Ranking Maps - Map of Addis Ababa with Health Facilities - Maps for the 2030 Census Round | - Strengthening Evidence-Based Policy and Decision-Making - Support ECA policy research work | Ongoing |
| ECA Web-Based Rapid Mapping tool | Ongoing – Draft stage | The tool will enable ECA staff and member-country experts to visualize spatial data without specialized GIS software or skills. | January 31, 2026 |
| Literature review of publications and information sources for monitoring investment trends in Africa | On going | Provides an evidence-based foundation to identify, analyze, and monitor investment trends in Africa, informing policy decisions, programme design, and alignment with continental and global development agendas. | January 31, 2026 |
| Preparation of the end or programme narrative and financial reports of the EU grant to ECA. | On going | Ensures accountability, transparency, and compliance with donor requirements while demonstrating results achieved and the effective use of resources. | January 31, 2026 |
| Data situation analysis platform for ECAStats | On going | To provide objective assessment of data availability, recency and completeness by topics, outputs and indicators | March 2026 |
| ECAStats enhancement | On going | Enhancement of data presentations to users: Currently developing data story page | February 2026 |
| Development of over 60 Geospatial Training Technical Manuals on Land, Water and the Environment | On-Going | Second Capacity Development Workshop on “Spatial Insights: Empowering Decision-Making and Transforming Knowledge into Action with Geospatial Intelligence.” 2 to 27 February 2025, Asmara, Eritrea | February 2026 |
| Land Statistics in Africa: The Value Proposition for Producing and Disseminating Development Indicator | On going | Support to the ACS Value Proposition of the Africa Beyond Numbers Series | March 2026 |

### 6. Flagship Publications / Reports

| Title |  | Type | Status | Expected Launch / Submission |
| --- | --- | --- | --- | --- |
| 2024 Africa SDGs Progress Report: Is Africa on track to achieve the 2030 Goals? |  | Flagship Report | Completed | January 2026; https://repository.uneca.org/entities/publication/0ee95b7b-8181-4661-bcf7-2fe8a4ccf760 |
| The 2026 Economic Report for Africa (ERA) – Chap 4, Data – The new oil fueling frontier technologies | Flagship Report | The report updated with comments from external reviewer and now shared with TICID for further review and subsequent publication | March 2026 |
| Preparation of ECA contributions to Africa Common positions - 57th UNSC |  | Report | Common position being drafted and country nomination to lead Africa’s position in the various sessions being identified. | January 2026 |
| Note of ACS for MFGD and other divisions on trade statistics |  | Short note | Updated the Draft note in preparation. First draft completed | 22 January 2026 |
| Africa Statistics Flash |  | Flagship Report | Completed | January 2026; https://www.uneca.org/data-and-statistics/africa-statistics-flash https://www.uneca.org/fr/donn%C3%A9es-et-statistiques/flash-statistiques-afrique |

### 7. Grants & RPTC progress

| Title of project | Type (Grant/ DA/ RPTC) | % Of resource utilization | Expiry date |
| --- | --- | --- | --- |
| DA 14 Project: 2225A - Resilient and agile national statistical systems to meet post-COVID-19 data needs to recover better | DA | 99.4% | 31st December 2025 (Expired) |
| DA 15 Project: 2326D - Quantifying South-South cooperation to mobilize funds for the Sustainable Development Goals | DA | 68.8% | June 30, 2026 |
| AfDB Grant - Capacity Building for Gender Statistics and Monitoring Systems (CB-GenSMS) Grant # S1-32HDM-000226 | XB | 94.4% | 31 December 2025 (Expired – NCE under discussion) |
| Bloomberg Grant (1) - To improve collection of birth and death data systems in Africa Grant # S1-32HDM-000247 | XB | 76.1% | 31 March 2027 |
| EAC - Eastern Africa Regional Statistics Program-for-Results (EARSP-for-R) Grant # S1-32HDM-000254 | XB | 69.3% | June 2027 |
| UNPDF - Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) Grant # S1-32HDM-000274 | XB | 0.9% | 30 September 2028 |
| Bloomberg Grant (2)- Developing Africa E-CRVS Shared Asset for Improvement of Digitalization of CRVS System in Africa Grant # S1-32HDM-000277 | XB | 8.3% | 30 June 2027 |
| UNFIP - Advancing data integration, innovation, and capacity in Africa (Africa Google Data Commons) Grant # S1-32HDM-000280 | XB | 15.5% | 30 June 2027 |

### 8. Key Challenges & Mitigation Measures

| Challenge | Implication | Proposed Solution / Action |
| --- | --- | --- |

9.  Member States Request

| Member State | Date Received | The Request Made | Is the request being considered? | Status Update | Additional Remarks |
| --- | --- | --- | --- | --- | --- |
| None |  |  |  |  |  |

10. Other Noteworthy Developments; Insert narrative bullet points on high-impact items, strategic engagements, resource mobilization updates, or inter-agency collaboration