# UNITED NATIONS ECONOMIC COMMISSION FOR AFRICA

## Weekly Division Update

Division/Section: 	African Centre for Statistics

Reporting Period: 	01- 08 February 2026

Submitted by: 		Samuel Kobina Annim, Director, African Centre for Statistics

Date Submitted:              9th  February 2026

| KPI Area | Target / Milestone | Progress This Week | Status (🟢/🟡/🔴) | Remarks |
| --- | --- | --- | --- | --- |
| IoA 1.1 (i) Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics (cumulative) (PPB 2026) Baseline (end of 2025): 46 Annual target (2026): 1 Cumulative target (47) = Baseline (46) + annual target (1) |  | Meeting of the Specialized Technical Group-4 on National Accounts and Price Statistics on 4-6 February 2026, in Hammamet (Tunisia) |  | The meeting updated Member State representatives on the new national accounts and Balance of Payments standards (2025 SNA and BPM7), assessed countries' support needs, and agreed on next steps. A Task Team will draft a continental roadmap for 2025 SNA implementation, and guidelines will be developed under the Pan-African Organization to harmonize economic practice |
| IoA (i) Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) PPB 2026 Baseline (end of 2025): 11 Annual target (2026): 14 Cumulative target (14) = Baseline (11) + annual target (3) |  |  |  |  |
| IoA 1: number of members of ECA adopting innovative technology applications in civil registration and vital statistics systems (cumulative)) Baseline (end of 2025): 3 Target (2026): 3 Cumulative: 6 |  | Selection of research papers for the CRVS Research Forum to be held in Bangkok in collaboration with ESCAP |  | Research on barriers to universal coverage of vital event registration. |
| Draft: (i) Number of ECA member States that have produced innovative statistical products for use in policy formulation, monitoring dissemination -non-PPB Baseline (end of 2025): 0 Annual target (2026): 8 Cumulative target (8) = Baseline (0) + Annual target (8) |  |  |  |  |

### 2. Major Initiatives & Projects in previous week)

| Initiative / Project | Key Milestone This Week | Next Steps | Lead Officer |
| --- | --- | --- | --- |
| Eastern Africa Regional Statistics Program-for-Results | Initial Finding Report reviewed by the EAC | Virtual Meeting with NISR and EAC scheduled for the 2ND week of February on the identified Verification protocols | Joseph |
| Digital Censuses | Preparedness assessment of the Population and Housing Census in Comoros | Developing the applications for the digital census | William Molla |
| Migration of GIS: infrastructure to the cloud |  |  | Peter Njagi Meron Kinfemichael Meazanesh Asres |
| Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) project |  |  | Andre Nonguierma |
| UN-PDF call for proposals | Awaiting the outcomes of the assessment from DPMO |  | Eileen, Ayenika Godheart Andre Nonguierma |
| Google project |  |  | Molla |
| Specialized Technical Group on Classification Training Workshop on classifications | Finalized the list of participants and the funders Updated the Agenda of the meeting | Administrative concerns of the meeting | Ali |
| Mid-term review of the National Strategy for the Development of Statistics of Seychelles, | Review of the self-assessment question Preparation of the field assessment mission | Undertaking the field assessment mission | Ilboudo Joseph, Leandre Ngogang, Angela Kiconco |
| Support to IGAD on the development of its second Regional Strategy for the Development of Statistics | Inception meeting with IGAD team to delineate ECA’s support | Preparation of the strategy development road map | Ilboudo Joseph, Leandre Ngogang, Angela Kiconco |
| Webinar series: Virtual Training on Forest Ecosystem Accounting – | 4th webinar (out of a series of 5) on 5 Feb 2026, focused on the greenhouse gas regulating services provided by forest ecosystems. | 5th Webinar is scheduled for 12 Feb 2026. | David |

3. Missions

| Team Member(s) | Destination | Dates | Objective | Key Outcomes | Funding Source (RB / RPTC / XB) |
| --- | --- | --- | --- | --- | --- |
| Ayenika Godheart and Peter Njagi | Asmara Eritrea | 2 to 6 of February | Second Capacity Development Workshop on “Spatial Insights: Empowering Decision-Making and Transforming Knowledge into Action with Geospatial Intelligence,” 2–27 February 2025, Asmara, EritreaA | Week one of the4Second Capacity Development Workshop on “Spatial Insights: Empowering Decision-Making and Transforming Knowledge into Action with Geospatial Intelligence,” 2–27 February 2025, Asmara, Eritrea sucessfully deliverd |  |

### 4. Workshops / Conferences Conducted

| Title | Date / Venue | Objective | Outcome / Follow-up |
| --- | --- | --- | --- |

### 5. Analytical Work (Ongoing or Completed)

| Topic | Status | Strategic Relevance | Expected Output Date |
| --- | --- | --- | --- |
| Daily Statistical facts and figures | On going | - Supports the modernization of statistical dissemination and enhances visibility of African data within the ECA | Ongoing |
| Analytical work on African Statistical Yearbook - ASYB | On going | - Contributes to evidence-based policymaking through comprehensive analysis and harmonized continental statistics | March 2026 |
| Informal cross border trade | On going | - Enhances understanding of regional trade dynamics and supports AfCFTA monitoring and regional integration. | June 2027 |
| Development of Compendium for Disaster-related Statistics | Ongoing | - Updating and refining the compendium with the hazard list - Harmonizes the indicators and provides a standardized framework for monitoring, reporting, and managing disaster risks across sectors | March 2026 |
| CRVS Applied Research and Training | Ongoing | - Identifying barriers to universal vital events registration | December 2026 |
| AfCIOT | Ongoing | - Data preparation for the integration of four additional countries: Kenya, Mauritania, Niger and Uganda - Preparation of the work plan for 2026 | February 2026 |
| Monitoring Water Resources of Africa | Ongoing - Time series analysis of Lake Chad extent | - Monitoring water resources in Africa is ongoing. - Timeseries analysis of Lake Chad extent was conducted using Google Earth Engine - Time series analysis of water bodies is vital to show long-term trends and seasonal patterns in water resources, enabling policymakers and managers to understand changes over time. It informs decision-making across environmental, socio-economic, and geopolitical dimensions. | Ongoing |
| Map Production, Spatial Analysis and Printing | - Continuous activity: - Poverty Ranking Maps - Map of Addis Ababa with Health Facilities - Maps for the 2030 Census Round | - Strengthening Evidence-Based Policy and Decision-Making - Support ECA policy research work | Ongoing |
| ECA Web-Based Rapid Mapping tool | Ongoing – Draft stage |  | January 31, 2026 |
| Preparation of the end or programme narrative and financial reports of the EU grant to ECA. | Ongoing. Submitted to PRMS for review |  | January 31, 2026 |
| Data situation analysis platform for ECAStats | On going | To provide objective assessment of data availability, recency and completeness by topics, outputs and indicators | March 2026 |
| ECAStats enhancement | On going | Enhancement of data presentations to users: Currently developing data story page | February 2026 |
| Development of over 60 Geospatial Training Technical Manuals on Land, Water and the Environment | On-Going | Second Capacity Development Workshop on “Spatial Insights: Empowering Decision-Making and Transforming Knowledge into Action with Geospatial Intelligence.” 2 to 27 February 2025, Asmara, Eritrea | February 2026 |
| Land Statistics in Africa: The Value Proposition for Producing and Disseminating Development Indicator | On going | Support to the ACS Value Proposition of the Africa Beyond Numbers Series | March 2026 |

### 6. Flagship Publications / Reports

| Title | Type | Status | Expected Launch / Submission |
| --- | --- | --- | --- |
| The 2026 Economic Report for Africa ERA) – Chap 4, ( Data – The new oil fueling frontier technologies | Flagship Report | The report updated with second step comments from external DES and now shared with MFGD and TICID for further review and subsequent publication | March 2026 |

### 7. Grants & RPTC progress

| Title of project | Type (Grant/ DA/ RPTC) | % Of resource utilization | Expiry date |
| --- | --- | --- | --- |
| DA 14 Project: 2225A - Resilient and agile national statistical systems to meet post-COVID-19 data needs to recover better | DA | 99.4% | 31st December 2025 (Expired) |
| DA 15 Project: 2326D - Quantifying South-South cooperation to mobilize funds for the Sustainable Development Goals | DA | 68.8% | June 30, 2026 |
| AfDB Grant - Capacity Building for Gender Statistics and Monitoring Systems (CB-GenSMS) Grant # S1-32HDM-000226 | XB | 94.4% | 31 December 2025 (Expired – NCE under discussion) |
| Bloomberg Grant (1) - To improve collection of birth and death data systems in Africa Grant # S1-32HDM-000247 | XB | 76.0% | 31 March 2027 |
| EAC - Eastern Africa Regional Statistics Program-for-Results (EARSP-for-R) Grant # S1-32HDM-000254 | XB | 63.9% | June 2027 |
| UNPDF - Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) Grant # S1-32HDM-000274 | XB | 1.4% | 30 September 2028 |
| Bloomberg Grant (2)- Developing Africa E-CRVS Shared Asset for Improvement of Digitalization of CRVS System in Africa Grant # S1-32HDM-000277 | XB | 26.3% | 30 June 2027 |
| UNFIP - Advancing data integration, innovation, and capacity in Africa (Africa Google Data Commons) Grant # S1-32HDM-000280 | XB | 15.8% | 30 June 2027 |

### 8. Key Challenges & Mitigation Measures

| Challenge | Implication | Proposed Solution / Action |
| --- | --- | --- |

9.  Member States Request

| Member State | Date Received | The Request Made | Is the request being considered? | Status Update | Additional Remarks |
| --- | --- | --- | --- | --- | --- |
| None |  |  |  |  |  |

10. Other Noteworthy Developments; Insert narrative bullet points on high-impact items, strategic engagements, resource mobilization updates, or inter-agency collaboration