# UNITED NATIONS ECONOMIC COMMISSION FOR AFRICA

## Weekly Division Update

Division/Section: 	African Centre for Statistics

Reporting Period: 	23 February –01 March 2026

Submitted by: 		Samuel Kobina Annim, Director, African Centre for Statistics

Date Submitted:              2nd  March 2026

| KPI Area | Target / Milestone | Progress This Week | Status (🟢/🟡/🔴) | Remarks |
| --- | --- | --- | --- | --- |
| IoA 1.1 (i) Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics (cumulative) (PPB 2026) Baseline (end of 2025): 46 Annual target (2026): 1 Cumulative target (47) = Baseline (46) + annual target (1) |  |  |  |  |
| IoA (i) Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) PPB 2026 Baseline (end of 2025): 11 Annual target (2026): 14 Cumulative target (14) = Baseline (11) + annual target (3) |  | - Burundi: Professional training on ArcGIS at Esri Rwanda has continued. - Mali: Follow-up on the recommendations of the Forum. Consultations have started with partners to organize a knowledge sharing for sustainable funding and return on investment of geospatial information. - Eritrea: Continued the capacity-building training on statistical and geospatial insights |  |  |
| IoA 1: number of members of ECA adopting innovative technology applications in civil registration and vital statistics systems (cumulative)) Baseline (end of 2025): 3 Target (2026): 3 Cumulative: 6 |  | - Developing functional and non-functional requirements for the digitalization of CRVS Systems |  | Bloomberg Grant |
| Draft: (i) Number of statistical products developed for use in policy formulation, monitoring and dissemination (cumulative) -non-PPB (2026) Baseline (end of 2025): 2 Annual target (2026): 4 Cumulative target (4) = Baseline (2) + Annual target (2) |  |  |  |  |

### 2. Major Initiatives & Projects in previous week)

| Initiative / Project | Key Milestone This Week | Next Steps | Lead Officer |
| --- | --- | --- | --- |
| Eastern Africa Regional Statistics Program-for-Results | Final Report Submitted and January Verificatio window closed | Follow up with EAC for April verification | Joseph |
| Digital Censuses | Weekly meeting with INSEED of Comoros and INSTAT of Madagascar on census preparations | Development of IT assets for the census | William Baakal |
| Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) project | - Continued the preparatory activities for the Regional Workshop for West African countries in Accra, Ghana: identification of participants; liaison with focal points; invitation letters, etc. | Continuing the preparatory activities for the organization of the regional workshop in Accra: Letters to national statistical offices | Andre Nonguierma |
| Google project | No update |  | Molla |
| Specialized Technical Group on Classification Training Workshop on classifications | No update |  | Ali |
| Mid-term review of the National Strategy for the Development of Statistics of Seychelles, | Workshop on the fields phase of the NSPS mid-term review, | Finalize and submit the mid-term review aide-mémoire to NBS senior management and the Board Finalize and submit the mid-term review report to NBS senior management and the Board | Ilboudo Joseph, Leandre Ngogang, Angela Kiconco |
| Support to IGAD on the development of its second Regional Strategy for the Development of Statistics | No update |  | Ilboudo Joseph, Leandre Ngogang, Angela Kiconco |
| Webinar series: Virtual Training on Forest Ecosystem Accounting – | Siers of webinar conducted from Octobber 2025 to Febuary 2026 | Follow up of the action points of the webinar | David |

3. Missions

| Team Member(s) | Destination | Dates | Objective | Key Outcomes | Funding Source (RB / RPTC / XB) |
| --- | --- | --- | --- | --- | --- |
| Laura Ngomegni, SRO-CA Issoufou Seidou Sanda, ACS Aissatou Sene, SRO-CA | Sao Tome and Principe, | 23-26 February 2026 | To strengthen the skills of national experts in designing statistical surveys for tourism data collection | - Strengthened technical and methodological capacity in tourism surveys (visitor, household, and enterprise) aligned with IRTS 2008 and TSA standards. - Enhanced skills in questionnaire design, sampling strategies, data integration with administrative sources, and use of digital tools (CAPI) for improved data quality. - Reinforced inter-institutional collaboration and provided key recommendations to improve coordination, sampling frames, geo-referencing, and alignment with TSA requirements. | RB |
| Tinfissi-Joseph Ilboudo, Léandre Ngogang, and Angela Kiconco | 16 – 20 February 2026 | Mahe, Seychelles | To conduct the field phase of the NSPS mid-term review, building on prior desk review and the NSDS self-assessment tool completed by NBS. | - Seychelles’ challenge is not strategy design but system activation, requiring stronger coordination, accountability, monitoring, and alignment with national planning and budgeting. - NSDS success depends on early institutionalization, legal backing, routine reporting, leadership commitment, and continuous dissemination to sustain ownership and institutional memory. - Partner support must be structured and aligned through formal coordination mechanisms to ensure the NSDS serves as the central platform for external assistance. | RPTC |

### 4. Workshops / Conferences Conducted

| Title | Date / Venue | Objective | Outcome / Follow-up |
| --- | --- | --- | --- |
| Workshop on strengthening the capacity of national experts in tourism-adapted survey methodologies– Methodological design | 23-26 February 2026 | To strengthen the skills of national experts in designing statistical surveys for tourism data collection | - Establish the Tourism Statistics Steering Committee and strengthen capacity for producing tourism statistics and TSA. - Improve data systems through tablets, tax/public finance data access, and an updated business register with geo-information. - Enhance coordination, awareness, and technical/financial support from partners. |

### 5. Analytical Work (Ongoing or Completed)

| Topic | Status | Strategic Relevance | Expected Output Date |
| --- | --- | --- | --- |
| Daily Statistical facts and figures | On going | - Supports the modernization of statistical dissemination and enhances visibility of African data within the ECA | Ongoing |
| Analytical work on African Statistical Yearbook - ASYB | On going | - Contributes to evidence-based policymaking through comprehensive analysis and harmonized continental statistics | March 2026 |
| Informal cross border trade | On going | - Enhances understanding of regional trade dynamics and supports AfCFTA monitoring and regional integration. | June 2027 |
| Development of Compendium for Disaster-related Statistics | Ongoing | - Updating and refining the compendium with the hazard list - Harmonizes the indicators and provides a standardized framework for monitoring, reporting, and managing disaster risks across sectors | March 2026 |
| CRVS Applied Research and Training | Ongoing | - Identifying barriers to universal vital events registration | December 2026 |
| AfCIOT | Ongoing | - Data preparation for the integration of four additional countries: Kenya, Mauritania, Niger and Uganda - Preparation of the work plan for 2026 - Updating trade data for AfCIOT | February 2026 |
| Monitoring Water Resources of Africa | Ongoing - Time series analysis of Lake Chad extent | - Monitoring water resources in Africa is ongoing. - Timeseries analysis of Lake Chad extent was conducted using Google Earth Engine - Draft technical report is generated - Time series analysis of water bodies is vital to show long-term trends and seasonal patterns in water resources, enabling policymakers and managers to understand changes over time. It informs decision-making across environmental, socio-economic, and geopolitical dimensions. | Ongoing |
| Map Production, Spatial Analysis and Printing | Continuous activity: - Maps of UN-GGIM: Africa Executive Board membership | - Strengthening Evidence-Based Policy and Decision-Making - Support ECA policy research work | Ongoing |
| ECA Web-Based Rapid Mapping tool | Ongoing – Draft stage | - Strengthens evidence-based decision-making, timeliness, and visibility of development interventions across member States | March 31, 2026 |
| Preparation of the end or programme narrative and financial reports of the EU grant to ECA. | Ongoing. Submitted to PRMS for review | - Donor accountability and dissemination of lesson learned and knowledge management | March31, 2026 |
| Data situation analysis platform for ECAStats | On going | - To provide objective assessment of data availability, recency and completeness by topics, outputs, and indicators | March 31 2026 |
| ECAStats enhancement | On going | - Enhancement of data presentations to users: Currently developing data story page | February 2026 |
| Development of over 60 Geospatial Training Technical Manuals on Land, Water and the Environment | On-Going | - Second Capacity Development Workshop on “Spatial Insights: Empowering Decision-Making and Transforming Knowledge into Action with Geospatial Intelligence.” 2 to 27 February 2025, Asmara, Eritrea | February 2026 |
| Land Statistics in Africa: The Value Proposition for Producing and Disseminating Development Indicator | On going | - Support to the ACS Value Proposition of the Africa Beyond Numbers Series | March 2026 |

### 6. Flagship Publications / Reports

| Title | Type | Status | Expected Launch / Submission |
| --- | --- | --- | --- |
| The 2026 Economic Report for Africa ERA) – Chap 4, ( Data – The new oil fueling frontier technologies | Flagship Report | The report updated with addressing comments from editors, acronyms and abbreviation list, and acknowledgement section and now shared with MFGD and TICID for further review and subsequent publication | March 31 2026 |

### 7. Grants & RPTC progress

| Title of project | Type (Grant/ DA/ RPTC) | % Of resource utilization | Expiry date |
| --- | --- | --- | --- |
| DA 15 Project: 2326D - Quantifying South-South cooperation to mobilize funds for the Sustainable Development Goals | DA | 68.8% | June 30, 2026 |
| AfDB Grant - Capacity Building for Gender Statistics and Monitoring Systems (CB-GenSMS) Grant # S1-32HDM-000226 | XB | 94.4% | 31 December 2025 (Expired – NCE requested Dec 2025) |
| Bloomberg Grant (1) - To improve collection of birth and death data systems in Africa Grant # S1-32HDM-000247 | XB | 79.3% | 31 March 2027 |
| EAC - Eastern Africa Regional Statistics Program-for-Results (EARSP-for-R) Grant # S1-32HDM-000254 | XB | 72.4% | June 2027 |
| UNPDF - Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) Grant # S1-32HDM-000274 | XB | 4.4% | 30 September 2028 |
| Bloomberg Grant (2)- Developing Africa E-CRVS Shared Asset for Improvement of Digitalization of CRVS System in Africa Grant # S1-32HDM-000277 | XB | 29.4% | 30 June 2027 |
| UNFIP - Advancing data integration, innovation, and capacity in Africa (Africa Google Data Commons) Grant # S1-32HDM-000280 | XB | 19.3% | 30 June 2027 |
| FAO - Short-term training on basic agricultural statistics and statistical data processing and presentation Grant # S1-32HDM-000285 | XB | 0.0% | 30 June 2026 |

### 8. Key Challenges & Mitigation Measures

| Challenge | Implication | Proposed Solution / Action |
| --- | --- | --- |

9.  Member States Request

| Member State | Date Received | The Request Made | Is the request being considered? | Status Update | Additional Remarks |
| --- | --- | --- | --- | --- | --- |

10. Other Noteworthy Developments; Insert narrative bullet points on high-impact items, strategic engagements, resource mobilization updates, or inter-agency collaboration