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[bookmark: _Hlk161644777]TEMPLATE FOR THE 2024 ANNUAL BUSINESS PLAN

Subprogramme: Data and Statistics 

	1. Objective 
	The objective, to which this sub-programme contributes, is to strengthen the production, dissemination and use of credible data, statistics and geospatial information  at the national,  regional and global  levels  for  evidence based  policy and  decision-making.

	2. Planned result area 1/Outcome
	RA1: Towards integrated geospatial information frameworks

	3. Indicator of Achievement (IoA)
	IoA 1: Number of countries developing and implementing an integrated geospatial information framework (cumulative)
· Baseline (end of 2023):19 [footnoteRef:1] [1: Benin, Burkina Faso, Burundi, Cameroon, Central African Republic, Congo, DR Congo, Ethiopia, Kenya, Lesotho, Madagascar, Mozambique, Morocco, Niger, Nigeria, Rwanda, Senegal, South Africa, Tunisia] 

· Target (2024): 2[footnoteRef:2] [2:  Eswatini and Comoros ] 

· Cumulative Target=   21  (baseline ( 19  ) + annual target ( 2 ) 

	4. Deliverables, Gender marker, Quarter, Funding source)
	Deliverable[footnoteRef:3] [3:  For consistency purposes, use the category of deliverables in the PPB and provide details under each category.  The list of deliverables should not be limited to the PPB but should cover deliverables under XB, DA, and RPTC.] 

Specify in parenthesis
1. the core function: TT, Convening, OP 
2. the SDG and target that each deliverable contributes to 
 
	Gender marker) (GEM 0, GEM 1, GEM 2a, GEM 2b)[footnoteRef:4]  [4:  2b = has gender equality and/or the empowerment of women and girls as the primary or principal objective; 2a= makes a significant contribution to gender equality and/or the empowerment of women and girls; 1= makes a limited contribution to gender equality and/or the empowerment of women and girls; 0= makes No contribution to gender equality and/or the empowerment of women and girls (but should do).
] 

	To be completed by
(shed the cell)
	Funding source and Budget
(In figures, USD)


	
	
	
	Q1
	Q2
	Q3
	Q4
	RB
	XB
	RPTC
	DA

	2.1. 
	Parliamentary documentation
	
	
	
	
	
	
	
	
	

	
	2.1.1. (Think Thank) (SDG.9, SDG.17) Geospatial information management to the Regional Committee of United Nations Global Geospatial Information Management for Africa at its eighth and ninth meetings
	1
	
	
	
	
	8,700
	
	
	

	
	2.1.2. (Think Thank) (SDG.17) Integration of geospatial and statistical data to the Statistical Commission for Africa at its seventh and eighth meetings
	1
	
	
	
	
	8,700
	
	
	

	4.2
	Substantive services for meetings
	
	
	
	
	
	
	
	
	

	
	4.2.1.  (Convening) h (SDG.11; SDG.17) 14th Session of United Nations Committee of Experts on Global Geospatial Information Management;
	1
	
	
	
	
	7,912
	
	
	

	
	4.2.2.  (Convening) (SDG.11; SDG.17) United Nations Group of Experts on Geographical Names
	1
	
	
	
	
	7,912
	
	
	

	
	4.2.3. (Convening) (SDG.9, SDG.17) Tenth Session of the Regional Committee of the United Nations Global Geospatial Information Management for Africa
	1
	
	
	
	
	59,650
	
	
	

	4.3. 
	Field and technical cooperation projects
	
	
	
	
	
	
	
	
	

	
	4.3.1. (Operations) (SDG.9, SDG.17) On developing geospatial information services in support of the implementation and tracking of the Sustainable Development Goals
	1
	
	
	
	
	
	50,000
	
	

	
	4.3.2. (Operations) (SDG.9, SDG.17) On guidelines for the implementation of the Integrated Geospatial Information Framework
	1
	
	
	
	
	
	50,000
	
	

	
	4.3.3. (Operations) (SDG.9, SDG.17) On strengthening the capacities of member States for the implementation of the African Geodetic Reference Frame
	1
	
	
	
	
	
	50,000
	
	

	4.4. 
	Seminars, workshops and training
	
	
	
	
	
	
	
	
	

	
	4.4.1.  (Convening) (SDG.17) Workshop on geospatial datasets for monitoring Sustainable Development Goals for national mapping agencies and statistical offices (5).
	1
	
	
	
	
	38,000
	
	
	

	
	4.4.1. (Convening) (SDG.17) Workshops on the strategy for the integration of statistical and geospatial information for national mapping agencies and statistical offices (5).
	1
	
	
	
	
	38,000
	
	
	

	
	4.4.2. (Convening) (SDG.9, SDG.17) Training events on the development of national action plans on the Integrated Geospatial Information Framework for national mapping agencies
	1
	
	
	
	
	38,000
	
	
	

	
	4.4.3. (Convening) (SDG.9, SDG.17) Training events on geospatial knowledge infrastructure with innovative geospatial responses and solutions for a post-pandemic recovery
	1
	
	
	
	
	38,000
	
	
	

	4.5. 
	Publication
	
	
	
	
	
	
	
	
	

	
	4.5.1. (Think Thank) (SDG.9, SDG.17)  UN-GGIM: Africa | Regional Activities report on geospatial information management in Africa
	1
	
	
	
	
	8,700
	
	
	

	
	4.5.2. (Think Thank) (SDG.17) Geocoding: A Strategic Pathway to the Modernization of Geospatial Information in Africa
	1
	
	
	
	
	8,700
	
	
	

	
	4.5.3. (Think Thank) (SDG.17) Assessment on the Availability of Geospatial Datasets for the Sustainable Development Goals in Africa
	1
	
	
	
	
	8,700
	
	
	

	4.6. 
	Technical materials
	
	
	
	
	
	
	
	
	

	
	4.6.1. (Operational) (SDG.9, SDG.17) African regional geospatial databases, online services and geoportals (1).
	1
	
	
	
	
	21,000
	
	
	

	
	4.6.2. (Operational) (SDG.17) African atlas of spatial statistics
	1
	
	
	
	
	3,000
	
	
	

	4.7. 
	Consultation, advice and advocacy
Advisory services and technical support
	
	
	
	
	
	
	
	
	

	
	4.7.1. (Operational) (SDG.9, SDG.17) Technical assistance in the establishment of national and regional spatial data infrastructures (NSDI) and integrated geospatial information framework (IGIF)
	1
	
	
	
	
	5,124
	
	
	

	
	4.7.2. (Operational) (SDG.9, SDG.17) Technical assistance in the integration of geospatial and statistical information, the implementation of the African Geodetic Reference Frame, the development of fundamental geospatial datasets themes and standards
	1
	
	
	
	
	4,812
	
	
	

	
	4.7.3. (Convening) | (Think Thank) | (Operations) (SDG.9, SDG.17) Technical assistance and advisory services in the implementation of global and regional initiatives and programmes (Group on Earth Observations, African initiative under the Global Earth Observation System of Systems, Global Monitoring for Environment and Security programme, Regional Centre for Mapping of Resources for Development, African Regional Institute for Geospatial Information Science and Technology, Digital Earth Africa and others)
	1
	
	
	
	
	10,248
	
	
	

	4.8. 
	Databases and substantive digital material
	
	
	
	
	
	
	
	
	

	
	4.8.1. (Operations) (SDG.9, SDG.17)  Geospatial databases, online applications, services and platforms; Africa Geoportal.
	1
	
	
	
	
	2,000
	
	
	

	4.9 
	Outreach programmes, special events and information materials
	
	
	
	
	
	
	
	
	

	
	4.9.1. (Convening) (SDG.17) Geographic Information Systems Day
	1
	
	
	
	
	3,000
	
	
	

	Additional narratives for each planned result/outcome

	5. Target countries/institutions/sub-regions
	Target Countries: 	All African countries. 
Partners:	African Union Commission, UN-GGIM, Regional Centre for Mapping of Resources for Development, African Regional Institute for Geospatial Information Science and Technology



[bookmark: _Hlk161645982]
	1. Planned result area 1/Outcome
	RA2: Towards digital transformation and modernization of statistical systems

	2. Indicator of Achievement (IoA)
	IoA 1: number of members of ECA that implemented the road map on digital transformation and modernized official statistics (cumulative)
· Baseline (end of 2023):11[footnoteRef:5]  [5:  Botswana, Madagascar, Nigeria, Zimbabwe, South Sudan, Mozambique, Uganda, Cameroun, Benin, Burundi, Zimbabwe, ] 

· Target (2024): 9
Cumulative Target=  (20)  baseline (  11 ) + annual target (9 )


	3. Deliverables, Gender marker, Quarter, Funding source)
	Deliverable[footnoteRef:6] [6:  For consistency purposes, use the category of deliverables in the PPB and provide details under each category.  The list of deliverables should not be limited to the PPB but should cover deliverables under XB, DA, and RPTC.] 

Specify in parenthesis
3. the core function: TT, Convening, OP 
4. the SDG and target that each deliverable contributes to 
 
	Gender marker) (GEM 0, GEM 1, GEM 2a, GEM 2b)[footnoteRef:7]  [7:  2b = has gender equality and/or the empowerment of women and girls as the primary or principal objective; 2a= makes a significant contribution to gender equality and/or the empowerment of women and girls; 1= makes a limited contribution to gender equality and/or the empowerment of women and girls; 0= makes No contribution to gender equality and/or the empowerment of women and girls (but should do).
] 

	To be completed by
(shed the cell)
	Funding source and Budget
(In figures)


	
	
	
	Q1
	Q2
	Q3
	Q4
	RB
	XB
	RPTC
	DA

	4.5. 
	Parliamentary documentation
	
	
	
	
	
	
	
	
	

	
	4.1.1. (Convening) Report on statistical development in Africa (SDG 17, Target 17.18)
	1
	
	
	
	
	10,000
	
	
	

	
	4.1.2. (Think-tank) Road map on transformation and modernization of official statistics in Africa. (SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	20,000
	
	
	

	
	4.1.3. (Think-tank) Report on SDGs indicators in Africa. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	10,000
	
	
	

	
	4.1.4. (Think-tank) Report on implementation of census monitoring dashboard in African countries. SDG 17, Target 17.18, 17.9, 16.9)
	2a
	
	
	
	
	10,000
	
	
	

	4.2. 
	Seminars, workshops, and training
	
	
	
	
	
	
	
	
	

	
	4.2.1. Statistical Commission for Africa. SDG 17, Target 17.18, 17.9)

	1
	
	
	
	
	100,000
	
	
	

	
	4.2.2. (Convening) Meeting of the United Nations Statistical Commission. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	20,000
	
	
	

	
	4.2.3. (Convening) Meeting of the Bureau of Statistical Commission for Africa (8). SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	25,000
	
	
	

	
	4.2.4. (Operational)Workshop on SDGs data reporting and management. SDG 17, Target 17.18, 17.9)  
	2a
	
	
	
	
	38,000
	
	
	

	
	4.2.5. (Operational)Workshop on Data science and Big Data. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	38,000
	
	
	

	
	4.2.6. Data validation workshop for the African Statistical Yearbook. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	38,000
	
	
	

	
	4.2.7. (Operational) Workshop to validate the report on the use of administrative data for statistical purposes in Africa. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	38,000
	
	
	

	
	4.2.8. (Operational) Webinar on the Dissemination and statistical literacy using new media: how, advantages and challenges. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	4,000
	
	
	

	
	4.2.9. (Operational) Webinar on administrative data for statistical purposes. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	4,000
	
	
	

	
	4.2.10. (Operational) National workshops on integrating administrative data in statistical production. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	40,000
	
	
	

	
	4.2.11. (Operational) Workshop on the road map for the transformation and modernization of official statistics in Africa – cross-fertilization with other global and regional initiatives. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	38,000
	
	
	

	4.3
	Publication
	
	
	
	
	
	
	
	
	

	
	4.3.1. (Think-tank) African Statistical Yearbook 2024. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	
	
	
	

	
	4.3.2. (Think-tank) African Pocket Book 2024. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	3,000
	
	
	

	
	4.3.3. (Think-tank)Africa Statistics Flash. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	3,000
	
	
	

	
	4.3.4. (OP) Report on the use of administrative data for statistical purposes in Africa. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	10,000
	
	
	

	
	4.3.5. Africa Sustainable Development Report. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	10,000
	
	
	

	4.4
	Technical materials
	
	
	
	
	
	
	
	
	

	
	4.5.1. (Think-tank)(ECAStats. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	4,000
	
	
	

	
	4.5.2. (think-tank) African UN data for Development. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	5,000
	
	
	

	
	4.5.3. (Convening)Census Monitoring Dashboard. SDG 17, Target 17.18, 17.9) 
	1
	
	
	
	
	5,000
	
	
	

	
	4.5.4. (Convening) Performance Data Management System. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	5,000
	
	
	

	
	4.5.5. (Operational) Guidelines for integrating the road map for the transformation and modernization of official statistics in the NSDSs. SDG 17, Target 17.18, 17.9)
	1
	
	
	
	
	20,000
	
	
	

	4.5
	Advisory services and technical support
	
	
	
	
	
	
	
	
	

	
	4.5.1. (Think-tank) African Statistical Yearbook. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	10,000
	
	
	

	
	4.5.2. (Operational) Digital population and housing censuses. SDG 17, Target 17.18, 17.9) 
	2a
	
	
	
	
	10,000
	
	
	

	
	4.5.3. (Operational) Data science capacity building. SDG 17, Target 17.18, 17.9) 
	1
	
	
	
	
	10,000
	
	
	

	
	4.5.4. (Think-tank) SDGs data management. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	10,000
	
	
	

	
	4.5.5. (Operational) Use of administrative data for statistical purposes. SDG 17, Target 17.18, 17.9)
	2a
	
	
	
	
	10,000
	
	
	

	Additional narratives for each planned result/outcome

	4. Target countries/instituions/sub-regions
	· ECA is planning technical assistance to 11 countries on digitalization and integration of data science initiatives: survey methodology and coordination of the national statistical system and statistical legislation (including administrative data systems and other sources) and technical assistance and advisory services to national statistical offices on SDGs dashboards. Additional countries will be supported in integrating administrative data in statistical production.
· Target countries to support for using administrative data for statistical purposes: Burundi, Cameroon, Lesotho, Namibia, Togo, Uganda

	1. [bookmark: _Hlk161646507]Planned result area 1/Outcome
	Result 3: Members of ECA produce and disseminate comparable economic statistics

	2. Indicator of Achievement (IoA)
	[bookmark: _Hlk161647112]IoA 1: Number of members of ECA that have adopted and applied the recommended international standards and methodology (System of National Accounts 20082 and extensions) in economic statistics (cumulative)
· Baseline (end of 2023): 37[footnoteRef:8] [8:  Benin, Burkina Faso, Burundi, Cabo Verde, Central African Republic, Democratic Republic of Congo, Djibouti, Equatorial Guinea, ESwatini, Ghana, Guinea-Bissau, Kenya, Lesotho, Liberia, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Republic of the Congo, Seychelles, Somalia, South Africa, South Sudan, Tanzania, The Gambia, Togo, Uganda, Zambia, Zimbabwe, Sao Tome and Principe, Nigeria, Cote d’ivoire, Cameroon, Senegal, Egypt
] 

· Target (2024): 5
· Cumulative target (42  ) = Baseline (37  ) + Annual target ( 5 )


	3. Deliverables, Gender marker, Quarter, Funding source)
	Deliverable[footnoteRef:9] [9:  For consistency purposes, use the category of deliverables in the PPB and provide details under each category.  The list of deliverables should not be limited to the PPB but should cover deliverables under XB, DA, and RPTC.] 

Specify in parenthesis
5. the core function: TT, Convening, OP 
6. the SDG and target that each deliverable contributes to 
 
	Gender marker) (GEM 0, GEM 1, GEM 2a, GEM 2b)[footnoteRef:10]  [10:  2b = has gender equality and/or the empowerment of women and girls as the primary or principal objective; 2a= makes a significant contribution to gender equality and/or the empowerment of women and girls; 1= makes a limited contribution to gender equality and/or the empowerment of women and girls; 0= makes No contribution to gender equality and/or the empowerment of women and girls (but should do).
] 

	To be completed by
(shed the cell)
	Funding source and Budget
(In figures)


	
	
	
	Q1
	Q2
	Q3
	Q4
	RB
	XB
	RPTC
	DA

	3.1. 
	Parliamentary documentation
	
	
	
	
	
	
	
	
	

	
	3.1.1. Implementation of the 2008 System of National Accounts to the Statistical Commission for Africa at its seventh and eighth meetings (SDG 17.19)
	1
	
	
	
	
	15,000
	
	
	

	3.2. 
	Seminars, workshops, and training
	
	
	
	
	
	
	
	
	

	
	3.2.1. (Think-tank) Regional seminar on the new system of national accounts (beyond GDP, surveys for GDP rebase, SUT/TiVA, etc.) (SDG 17.19,17.10,17.11.17.12,13)
	1
	
	
	
	
	55,000
	
	
	

	
	3.2.2. Training events on big data and data science for the modernization of the production of economic statistics (SDG 9.5, 17.18,17.17)
	1
	
	
	
	
	
	55,000
	
	

	
	3.2.3. (Convening) Regional seminar on agriculture statistics (SDG 17.18,17.17), (SDG 2.3, 2.C)
	1
	
	
	
	
	
	55,000
	
	

	
	3.2.4. (Convening) Regional seminar on energy statistics (SDG 17.18,17.17), (SDG 7.8)
	1
	
	
	
	
	
	55,000
	
	

	
	3.2.5. (Operational Advisory expert group meeting on national accounts (SDG 17.19,17.10,17.11.17.12,13)
	1
	
	
	
	
	55,000
	
	
	

	
	3.2.6. (Operational) Training events on methods of environmental statistics and environmental economic accounting for national agencies responsible for the compilation of environmental economic accounts (SEEA-CF, SEEA-ecosystem, etc.) (SDG 17.19,17.10,17.11.17.12,13) (SDG 13.3)
	1
	
	
	
	
	55,000
	
	
	

	
	3.2.7. (Convening) Consultative meeting on strengthening and harmonization of economic statistics in Africa. (SDG 17.6,17.18,17.17),
	1
	
	
	
	
	
	55,000
	
	

	
	3.2.8. (Convening) Expert group meeting on environmental-economic accounting (SDG 17.19,17.10,17.11.17.12,13) (SDG 13.3)
	1
	
	
	
	
	55,000
	
	
	

	
	3.2.9. Technical workshop on environmental statistics SDG 13.3)
	1
	
	
	
	
	 
	55,000
	
	

	
	3.2.10. Technical workshop on environmental-economic accounting (SDG 13.3)
	1
	
	
	
	
	 
	55,000
	
	

	4.3
	Publication
	
	
	
	
	
	
	
	
	

	
	4.3.1. (Think-tank) ECA Price Watch Centre: Update, analysis, and dissemination (SDG 17.19,17.10,17.11.17.12,13)
	1
	
	
	
	
	
	10,000

	
	

	
	4.3.2. (Think-tank) An on-line repository: “ECA Price Watch Centre”: Data in the portal are updated on a monthly basis(SDG 17.19,17.10,17.11.17.12,13)
	1
	
	
	
	
	10,000

	
	
	

	
	4.3.3.  (Think-tank)Compendium of intra-African and foreign trade statistics. (SDG 17.19,17.10,17.11.17.12,13)
	1
	
	
	
	
	10,000
	
	
	

	4.4
	Technical materials
	
	
	
	
	
	
	
	
	

	4.5.
	Advisory services and technical support
	
	
	
	
	
	
	
	
	

	
	4.5.1. (Operational) on the development of supply-use tables (SUTs), intra-regional input-output table (IOT) and trade-in-value-added (TiVA) model   
	1
	
	
	
	 
	10,000
	100,000
	120,000
	

	
	4.5.2.  (Operational) on technical assistance on GDP updating and rebasing in member States. (SDG 17.19,17.10,17.11.17.12,13)
	1
	
	
	
	
	10,000
	100,000
	120,000
	

	
	4.5.3. (Operational) on leading African countries to participate in the global updating and related testing of the 2008 SNA programme. . (SDG 17.19,17.17)
	1
	
	
	
	
	10,000
	100,000
	120,000
	

	
	4.5.4.  (Operational) on consumer price index (CPI): data collection, compilation, and application. . (SDG 17.19,17.17)
	1
	
	
	
	
	10,000
	100,000
	120,000
	

	
	4.5.5. (Operational) Development of a data science campus. SDG 17.19,17.17)
	1
	
	
	
	
	10,000
	100,000
	120,000
	

	Additional narratives for each planned result/outcome

	5. Target countries/instituions/sub-regions
	· Technical or online assistance and advisory services on GDP Rebasing programme : Republic of the Congo, Democratic Republic of the Congo, Eswatini, Gabon, Sao Tome and Principe.
· Leading African countries to participate in the global updating and related testing of the 2008 SNA programme: All countries
· Development of supply-use tables (SUTs), intra-regional input-output table (IOT) and trade-in-value-added (TiVA) model: Eswatini, Namibia and all countries with SUT available
· TiVA project, technical assistance, and advisory services: Cameroon, Cote d’Ivoire, Egypt, Nigeria, and Senegal.
· Consumer price index (CPI): 	All countries
· Support supply and uses tables ( SUTs) and Trade in value added (TiVA) compilation : OECD and WTO; and Office for National Statistics, UK will contribute to technical assistance activities
· CPI data collection:  with partners to provide technical expertise and share practical experiences (INSEE France, ONS UK, SurveyCTO, Global Partnership) 
· GDP rebasing and updating programme of SNA: AFRISTAT, AfDB, IMF, RECS, UNSD and World Bank and countries will be coordinating the intervention of different partners. 





	1. [bookmark: _Hlk161647229]Planned result area 1/Outcome
	RA4 Increased visibility through civil registration and good legal identity

	2. Indicator of Achievement (IoA)

	IoA1: Total number of countries that register at least 50 percent of births within 24 months (cumulative)
· Baseline (end of 2023):16[footnoteRef:11]  [11:  2023 (5): Ghana, Djibouti, Lesotho, Malawi Kenya; 2022 baseline (11): Equatorial Guinea, Sudan, Togo, Chad, Somalia, Guinea Conakry, Eswatini, Democratic Republic of Congo, Angola, Burundi, Burkina Faso, ] 

· Target (2024): 5[footnoteRef:12] [12: 

] 

· Cumulative target (21) = baseline (16) + annual target (5)
IoA2: Cumulative number of national statistical authorities formulated plans to improve the availability of data needed for gender-responsive trade policies
· Baseline (end of 2023): 4 (0)
· Target (2024): 4[footnoteRef:13] [13:  Mozambique, Zimbabwe, Burundi, South Sudan; Continuous activity] 

· Cumulative target ( 4  ) =Baseline (  0 ) + annual target ( 4 )

	3. Deliverables, Gender marker, Quarter, Funding source)
	Deliverable[footnoteRef:14] [14:  For consistency purposes, use the category of deliverables in the PPB and provide details under each category.  The list of deliverables should not be limited to the PPB but should cover deliverables under XB, DA, and RPTC.] 

Specify in parenthesis
7. the core function: TT, Convening, OP 
8. the SDG and target that each deliverable contributes to 
 
	Gender marker) (GEM 0, GEM 1, GEM 2a, GEM 2b)[footnoteRef:15]  [15:  2b = has gender equality and/or the empowerment of women and girls as the primary or principal objective; 2a= makes a significant contribution to gender equality and/or the empowerment of women and girls; 1= makes a limited contribution to gender equality and/or the empowerment of women and girls; 0= makes No contribution to gender equality and/or the empowerment of women and girls (but should do).] 

	To be completed by
(shed the cell)
	Funding source and Budget
(In figures)


	
	
	
	Q1
	Q2
	Q3
	Q4
	RB
	XB
	RPTC
	DA

	4.1
	Parliamentary documentation
	
	
	
	
	
	
	
	
	

	
	3.1.1. (Think-tank) Implementation of civil registration and vital statistics to the seventh Conference of African Ministers responsible for Civil Registration
(SDG: Goal 16, Target 16.9)
	2a
	
	
	
	
	8700
	
	
	

	
	3.1.2. (Think-tank) Report on Conference of African Ministers responsible for Civil Registration	
(SDG: Goal 16, Target 16.9)
	1
	
	
	
	
	8700
	
	
	

	
	3.1.3. (Convening)Substantive services for meetings Conference of the African Ministers responsible for Civil Registration. (SDG: Goal 16, Target 16.9)
	2a
	
	
	
	
	7,912
	
	
	

	
	3.1.4. [bookmark: _Hlk161736643](Convening) Progress in population and housing censuses to the Statistical Commission for Africa at its seventh and eighth meetings (SDG: Goal 17 Target 17.19)

	2a
	
	
	
	
	7,912
	
	
	

	
	3.1.5. (Think-tank) State of a gender perspective and social development statistics to the Statistical Commission for Africa at its seventh and eighth meetings (SDG: Goal 17 Target 17.19)
	2b
	
	
	
	
	7,912
	
	
	

	4.2
	Seminars, workshops and training
	
	
	
	
	
	
	
	
	

	
	4.2.1.  (Convening)Workshop on population and housing censuses and progress towards the 2021 population and housing censuses for experts and managers of national statistical offices and planning commission (SDG: Goal 17 Target 17.19)
	2a
	
	
	
	
	
	50,000
	
	

	
	4.2.2.  (Convening) Regional workshops on gender statistics for experts in national statistical offices and line ministries. (SDG: Goal 17 Target 17.19)
	2b
	
	
	
	
	
	25,000
	
	25,000

	
	4.2.3.  (Convening)Workshops on civil registration and vital statistics for experts of national ministries responsible to produce civil registration and vital statistics data
(SDG: Goal 16, Target 16.9); 
	2a
	
	
	
	
	
	50,000
	
	

	
	4.2.4. (Convening)Workshop on measuring and monitoring Sustainable Development Goal indicators related to demographic and social statistics for experts in national statistical offices
(SDG: Goal 17 Target 17.19)
	2a
	
	
	
	
	
	50,000
	
	

	
	2.2.5.  (Convening) National technical workshops in DA12 on trade and gender countries to discuss the conceptual framework for measuring gender and trade as well statistical guidelines prepared based on this conceptual framework and then use them to identify national policy data needs, identify data availability, and discuss possible actions to address the gaps and challenges. 
(SDG: Goal 17 Target 17.19) ; (SDG: Goal 16, Target 16.9);
	2b
	
	
	
	
	
	
	
	50,000

	
	4.2.6. (Convening)Regional wrap-up workshop to share DA12 findings pilots, progress of national work and planned actions to develop and use statistics to formulate more gender-responsive trade policy.
(SDG: Goal 17 Target 17.19)
	2b
	
	
	
	
	
	
	
	50.000

	4.3
	Publication
	
	
	
	
	
	
	
	
	

	
	4.3.1.(Think-tank) E-census Handbook on Implementation of 2020 Round of Population and Housing Census in Africa (SDG: Goal 17 Target 17.19)
	2a
	
	
	
	
	10,000
	
	
	

	4.4
	Technical materials
	
	
	
	
	
	
	
	
	

	
	4.8.2. (think-thank) statistical guidelines and other material for the compilation of trade and gender statistics. (SDG: Goal 17 Target 17.19)
	2b
	
	
	
	
	
	
	
	15,000

	4.5
	Advisory services and technical support
	
	
	
	
	
	
	
	
	

	
	4.5.1. (Operational)Technical advice on the 2023 round of population and housing censuses for member States in Africa (SDG: Goal 17 Target 17.19)
	2a
	
	
	
	
	10.000
	
	150,000
	

	
	4.5.2. (Operational)Technical advice to member States on the implementation of civil registration frameworks and systems. SDG: Goal 16, Target 16.9
	2a
	
	
	
	
	10,000
	100,000
	120,000
	

	
	4.5.3. (Operational)Advice on the development and management of civil registration and vital statistics strategic plans. SDG: Goal 16, Target 16.9
	2a
	
	
	
	
	10,000
	100,000
	120,000
	

	
	4.5.4. (Operational)Advice on the production and dissemination of gender statistics. (SDG: Goal 17 Target 17.19)
	2b
	
	
	
	
	10,000
	100,000
	120,000
	

	
	4.5.5. (Convening)Advocacy to strengthen the gender statistics focal point network. (SDG: Goal 17 Target 17.19)
	2b
	
	
	
	
	
	50,00
	
	

	
	4.5.6. (Convening)Advocacy to strengthen population and housing censuses. (SDG: Goal 17 Target 17.19)
	2a
	
	
	
	
	10,000
	10,000
	100,000
	

	
	4.5.7. (Operational)Advisory missions to support DA12 countries to review data gaps, collate statistics and/or prepare action plans for gender-responsive trade policy. (SDG: Goal 17 Target 17.19)
	2b
	
	
	
	
	
	
	
	50,000

	
	4.5.8.  (Think-tank) Pilot test of the draft framework with countries at different stages of statistical development. (SDG: Goal 17 Target 17.19)
	1
	
	
	
	
	
	
	
	50,000

	Additional narratives for each planned result/outcome


	5. Target countries/instituions/sub-regions
	CRVS mentorship program: 	South Sudan, Burundi, Ghana, 
Data & Statistics for more gender-responsive trade policies in Africa: Cameroon, Kenya, Senegal, and Zimbabwe)
Census undertakings:  Burundi, Nigeria and Djibouti
Capacity Building for Gender Statistics and Monitoring Systems (CB-GenSMS): Burundi, Mozambique, South Sudan, and Zimbabwe
.









	Additional narratives at subprogramme level

	6. Strategic directions 
		☒   1. Build
The subprograms aims to building the capacity of MS in improving agricultural and rural statistics, Economic statistics and National Account and environmental statistics for compiling environmental economic accounting
	☒  2. Formulate
	☐  3. Design
The subprogram will design Trade in Value Added data base as part of improving capacity. Strengthening database: NA, CPI and inflation, Agriculture, Energy and SUTs

	☐  4. Integrate
	☒  5. Advocate
Advocate MS on strengthening and harmonization of economic statistics in Africa




	7. Medium term programme framework

	
	☐   1. An Africa that invests in human potential for sustainable development
	☐  2. An integrated Africa
	☒  3. An innovative, connected Africa
	☐  4. An Africa of sustainable, productive industries and economies
	☐  5. An Africa of stable and effective institutions




	8. Strategic Tracks
	[bookmark: _Hlk151573914]
	[bookmark: _Hlk151574050]☐  Track 1: Strengthening macroeconomic policy including issues of sustainable financing, debt management, and interface with governance issues.

	☒  Track 2:  Boosting the implementation of the African Continental Free Trade Area (AfCFTA), sustainable industrialization and economic diversification, job creation and poverty reduction;
	☒ Track 3: Enhancing resilience through climate action, energy just transition, green and blue economy, data, and digital transformation.




	9. Resident Coordinator System and RCP/O/IBCs[footnoteRef:16] and task forces [16:  O/IBC 1 – "Strengthened Integrated Data and Statistical Systems for Sustainable Development and The Africa We Want"; O/IBC 2 – "Ensuring effective and efficient macroeconomic management and accelerated inclusive, economic transformation and diversification"; O/IBC 3 – "Innovation, Digitalization, Youth and Transforming Education"; O/IBC 4 – "Fostering Climate Action, Resilience, and Food Systems"; O/IBC 5 – "Towards Peace, Security, Respect of Human Rights, and Forced Displacement"; O/IBC 6 – "Sub-regional Initiatives and Strategies (cross-cutting)"
] 

	Resident Coordinator System:
· The RC and UCTs will have three roles: to co-ordinate with ECA and pilot countries and provide administrative and logistic support for regional conferences and technical assistance missions to countries; working together with the technical team of ECA, to help provide the technical guidance for the countries to carry out the project; and to monitor the progress of project implementation in countries.

Opportunities and Issue Based Coalitions:
OIBC1: support to implementation of the UN Africa data and statistics strategy and operationalization of the Africa UN Data for Development Platform. 
· “Strengthened integrated data and statistical systems for sustainable development” This will be done through harmonizing the very concepts, definitions and classifications used across statistical sources, following national and international standards. The harmonization process shall have a unreserved contribution to ease the regional collaboration and platforms in the process of collecting and utilizing statistical data across the continent 
· on integrated data and statistical systems for sustainable development and the Africa We Want
OIBC 4 – Leveraging new technologies and enabling digital transition


	10. Partnerships 
	· Implementation of the 2008 SNA in Africa; working with the AGNA: AUC, AfDB, AFRISTAT, RECs, UNSD
· Capacity building programme on supply and uses tables ( SUTs) and Trade in value added (TiVA): jointly carried out together with OECD and WTO; and Office for National Statistics, UK contributes to technical assistance activities; 
· Capacity building programme on CPI data collection: Various international organizations and development partners to provide technical expertise and share with practical experiences (INSEE France, ONS UK, SurveyCTO, Global Partnership) 
· ECA Price Watch Centre (PWC): ECA’s substantive Divisions and RSOs
· GDP rebasing missions and update programme of SNA  carried out by ECA along with other partners (AFRISTAT, AfDB, IMF, RECS, UNSD and World Bank) and the countries coordinated the intervention of different partners.  
· Contribution Agreement EU/Eurostat/UNECA on Support to monitoring of SDGs and statistics in Africa
· UNFPA on the implementation of Censuses. UNICEF, UNDESA, and UNDP on the coordination of the United Nations Legal Identity Agenda
· UN Women on Gender Statistics
· AUC and AfDB on the Conference of Ministers Responsible for Civil Registration

	11. Gender considerations 
	
· Gender will be mainstreamed in all processes of collecting, managing, and analysing economic, social and demographic data. Statistical indicators will be disaggregated by gender. The subprogramme is implementing a special project which promotes the development and implementation of gender-responsive trade policies in four countries. The support will continue to strengthen the capacity of the targeted countries and will be diffused in other members States in the years to come.
· Support in mainstreaming gender in the national strategy for the development of statistics will be extended to member States. This assistance aims to ensure that the gender dimension is considered in statistics planning and statistical operations and that there is a continuous dialogue between gender policymakers and producers of official statistics. Availability of quality gender responsive trade statistics is contributing to   the   monitoring the SDGs 1, 2, 4, 5,8, 10 and 17

	12. Human rights mainstreaming
	Human rights will be mainstreamed in all deliverables of result areas. 
· Strong civil registration system in Africa contributing to SDG 16.9 targets of 100 percent birth registration and establishment of legal identity for children, and 80 percent death registration will be sustained from the right holder’s approach to support individual and family level rights. 
· The CRVS law which had biased and prejudice inclinations towards accessing legal documents for women and their children will be addressed through continued CRVS mentorship and capacity development supports
· The subprogram continue to supporting MS with UNICEF and PARIS21 in developing a Toolkit for mainstreaming Child Rights into strategic planning for official statistics as reference points for data producers, planners, and users to agree on how Child Rights can be best integrated into planning for official statistics. 

	13. Disability inclusion
	
	☒   0. Does not substantially contribute to the rights of persons with disabilities and disability inclusions but persons with disabilities benefits from the outputs
	☐  1. Contributes to the rights of persons to the rights of persons with disabilities and disability inclusion in a significant way
	☐  2. Rights of persons with disabilities and disability inclusions are the principal or primary objective of the work of the SP





	14. ES Compact
	Promote technology, innovation, digital transformation, and data and statistics as transformative elements in   advancing the achievement of the goals of Agenda 2030 and the 2063 Agenda.
	Enhanced capacities of Member States for the development of national Digital Transformation Strategy and strategies for national digital ID systems.

	Enhanced capacities of Member States to develop and implement integrated geospatial information frameworks.

	Strengthened production, dissemination and use of credible data, statistics and geospatial information at the national, and regional levels for evidence based policy and decision-making.








ANNEX: RISK SECTION 

The Risk Section included in the ABP is a summary of the information detailed in Division, SRO and IDEP risk profiles. The Detailed risk profiles are completed in coordination with the DoA/Risk Management Unit. Division, SRO and IDEP risks should be aligned to their objectives and Planned results as well as the ECA Corporate Risk register and treatment plans. Quarterly reporting is expected from all Division, SRO, and IDEP to update stakeholders on the implementation of the prioritized risk treatment plans. 
Below is the summarized template.

	RISK DEFINITION (Aligned to the Division, SRO & IDEP objective & planned results, as well as the ECA Corporate Risk Register)
	CAUSES/ RISK DRIVERS (Underlying or fundamental reason(s) why the risk is happening)
	RESIDUAL RISK RATING(Probability rating   less Internal Controls effectiveness rating) Multiplied by (Impact rating less Internal controls effectiveness rating)
	RISK TREATMENT ACTION(S) 
(These are actions to be taken to reduce the residual risk)
	RESPONSIBLE PERSON(S) (Party(ies) responsible for implementation of the treatment action)
	IMPLEMENTATION TIMELINE 
(Please include dates when the treatment plans will be implemented)

	Limited and inaccessible data on socio-economic and GIS statistics.





	Low political commitment in support of socio-economic and Geo Spatial Data and statistics.
	6

	Political engagement at top management


	ACS
	Ongoing, throughout the year 2024

	
	Limited funding provided in the country's budgets for data collection, analysis, dissemination and use.
	12
	Engagement with partners to mobilize more resources
	ACS
	Ongoing, throughout the year 2024

	
	Limited knowledge on funds provided by other partners for data collection, analysis, dissemination and use
	4
	create additional staffing on regular and staff training on new skills.

	ACS/HRMS
	Ongoing, throughout the year 2024

	
	Political instability that limits surveys and census.
	12
	Political engagement at top management

	ACS
	Ongoing, 2024

	
	Administrative data sources are not good quality, usable and comprehensive.
	9
	Strengthen national statistical systems of member states through forging partnerships with other pan-African organizations and international partners.

	ACS
	Ongoing, throughout the year 2024

	
	Limited skilled man power to undertake data collection in member states
	9
	Strengthening capacity building programs in member states in collaboration with partners.

	ACS/HRMS
	Ongoing, throughout the year 2024

	
	Pandemics that have led to postponement and redeployment of funds meant for data collection
	4
	
	
	Ongoing, throughout the year 2024

	Limited capacity of member states in data collection, analysis, dissemination and use
	Inadequate staffing of ACS (delayed recruitment, posts disappearing, guidelines of the institution limits the recruitment of consultants for a longer time)
	12
	Create additional staffing on regular and staff training on new skills. 

	ACS/HRMS
	Ongoing, throughout the year 2024

	Limited national data availability for reporting on the SDG and Agenda 2063

	Inadequate incentive and motivation for member states to provide data and responses when requested

	8
	Engagement with member states at top management level.

	ACS
	Ongoing, throughout the year 2024

	Lack of financial and adequate human resources to deliver the set outputs  

	Lack of clarity in priorities (member states, based on not their needs but based on the availability of funds)

	6
	Strengthen coordination and collaboration with RECs, RCs, and UNCTs to enhance project delivery and collaboration

	ACS
	Ongoing, throughout the year 2024

	Limited capacity of member states in data collection, analysis, dissemination and use 

	Changes by Member States during course of forming agreements resulting in low political commitment in countries of implementation
	12
	Increase awareness and advocacy on coordination of national statistical systems; continuous dialogue and engagement with Member States to better assist them in their needs

	Member states, NSO
	Ongoing, throughout the year 2024

	Limited capacity of member states to transform and modernize their statistical systems.

	Limited resource mobilization in support of countries request for technical assistance.
	9
	· Strengthen national statistical systems   of member states through forging partnerships with other Pan-African organizations and international partners.
· Engagement with partners to mobilize more resources
	ACS
	Ongoing, throughout the year 2024

	Planned/targeted performance may not be achieved

	Inadequate performance measurement and alignment of Division outputs
	9
	Create key performance indicators(KPIs) and implement which are linked to the divisions outputs(objectives).
	ACS
	Ongoing, throughout the year 2024

	
	Lack of adequate financial resources to deliver the set outputs (ACS) to reflect countries support
	9
	Engagement with partners to mobilize more resources

	ACS
	Ongoing, throughout the year 2024

	
	Lack of adequate human resource to deliver the set outputs
	9
	Create additional staffing on regular and staff training on new skills.
	ACS
	Ongoing, throughout the year 2024

	Member states will not be able to produce quality data which impact the meagre resources that member states have

	Continuous development of digital tools to match the demands of member states (too much requests too little resources and time)6
	9
	Engagement with partners to mobilize more resources and create additional staffing on regular and staff training on new skills.
	ACS
	Ongoing, throughout the year 2024
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