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TEMPLATE FOR THE 2023 ANNUAL BUSINESS PLAN
(to be replicated for each planned result area)

Subprogramme: Data and Statistics 

	1. Objective
	The objective, to which this sub-programme contributes, is to strengthen the production, dissemination and use of credible data, statistics and geospatial information  at the national,  regional and global  levels  for  evidence based  policy and  decision-making.

	2. Planned result area 1/Outcome
	RA1: Increased visibility through civil registration and good legal identity

	3. Indicator of Achievement (IoA)
	IoA1: Total number of countries that register at least 50 percent of births within 24 months (cumulative)/ Number of countries that register at least 50% of births within the national legally prescribed period
· Baseline (end of 2022): 11[footnoteRef:1] [1:  Eswatini, Somalia, Togo, Ghana, Burkina Faso, Equatorial Guinea, Sudan, Guinea Conakry, Democratic Republic of Congo, Malawi and Angola] 

· Target (2023): 5[footnoteRef:2] [2:  Djibouti, South Sudan, Lesotho, Burundi, Chad] 

· Cumulative target (16) = baseline (11) + annual target (5)
IoA2: Cumulative number of national statistical authorities formulated plans to improve the availability of data needed for gender-responsive trade policies
· Baseline (end of 2021): 0
· Target (2022): 4[footnoteRef:3] [3:  Cameroon, Kenya,  Senegal and Zimbabwe] 

· Cumulative target (4) =Baseline (0) + annual target (4)

	4. Deliverables, Gender marker, Quarter, Funding source)
	Deliverable[footnoteRef:4] [4: ] 

(Specify the core function: TT, Convening, OP in a parenthesis)
 
	Gender marker (0-3) 
	To be completed by
(shed the cell)
	Funding source
(not in figures)


	
	
	
	Q1
	Q2
	Q3
	Q4
	RB
	XB
	RPTC
	DA

	1
	Parliamentary documentation
	
	
	
	
	
	
	
	
	

	
	1.1. (Think-tank) Implementation of civil registration and vital statistics to the Sixth Conference of African Ministers responsible for Civil Registration 	
	3
	X
	
	
	
	X
	X
	X
	

	
	1.2. (Think-tank) Report on Conference of African Ministers responsible for Civil Registration	
	3
	X
	
	
	
	X
	X
	X
	

	
		
1.3. (Convening)Substantive services for meetings Conference of the African Ministers responsible for Civil Registration
	3
	X
	
	
	
	X
	X
	X
	

	2
	Seminars, workshops and training
	
	
	
	
	
	
	
	
	

	
	2.1. (Convening)Workshop on population and housing censuses and progress towards the 2021 population and housing censuses for experts and managers of national statistical offices and planning commission
	3
	
	X
	
	
	
	X
	
	

	
	2.2. (Convening) Regional workshops on gender statistics for experts in national statistical offices and line ministries

	3
	
	
	X
	
	
	X
	
	X

	
	2.3. (Convening)Workshops on civil registration and vital statistics for experts of national ministries responsible to produce civil registration and vital statistics data
	3
	X
	
	
	
	
	X
	
	

	
	2.4. (Convening)Workshop on measuring and monitoring Sustainable Development Goal indicators related to demographic and social statistics for experts in national statistical offices
	3
	
	X
	
	
	
	X
	
	

	
	2.5. (Convening) National technical workshops in DA12 on trade and gender countries to discuss the conceptual framework for measuring gender and trade as well statistical guidelines prepared based on this conceptual framework and then use them to identify national policy data needs, identify data availability, and discuss possible actions to address the gaps and challenges. 
	3
	X
	
	
	
	
	
	
	X

	
	2.6. (Convening)Regional wrap-up workshop to share DA12 findings pilots, progress of national work and planned actions to develop and use statistics to formulate more gender-responsive trade policy.
	3
	
	X
	
	
	
	
	
	X

	3
	Publication
	
	
	
	
	
	
	
	
	

	
	3.1.(Think-tank) E-census Handbook on Implementation of 2020 Round of Population and Housing Census in Africa
	2
	
	
	
	
	
	
	
	

	4
	Technical materials
	
	
	
	
	
	
	
	
	

	
	4.1. (think-thank) statistical guidelines and other material for the compilation of trade and gender statistics. 
	3
	
	X
	
	
	
	
	
	X

	5
	Advisory services and technical support
	
	
	
	
	
	
	
	
	

	
	5.1. (Operational)Technical advice on the 2023 round of population and housing censuses for member States in Africa 
	2
	X
	
	
	
	X
	X
	X
	

	
	5.2. (Operational)Technical advice to member States on the implementation of civil registration frameworks and systems
	2
	X
	
	
	
	X
	X
	X
	

	
	5.3. (Operational)Advice on the development and management of civil registration and vital statistics strategic plans
	2
	
	X
	
	
	X
	X
	X
	

	
	5.4. (Operational)Advice on the production and dissemination of gender statistics
	3
	
	X
	
	
	X
	X
	X
	X

	
	5.5. (Think tank) Advocacy to strengthen the gender statistics focal point network
	3
	X
	X
	
	
	
	X
	
	

	
	5.6. (Think tank)Advocacy to strengthen population and housing censuses
	3
	
	X
	
	
	X
	X
	X
	

	
	5.7. (Operational)Advisory missions to support DA12 countries to review data gaps, collate statistics and/or prepare action plans for gender-responsive trade policy. 
	3
	X
	X
	
	
	
	
	
	X

	
	5.8.  (Think-tank) Pilot test of the draft framework with countries at different stages of statistical development 
	3
	X
	X
	
	
	
	
	
	X

	Additional narratives for each planned result/outcome

	5. SDG tagging
	· Strong civil registration system in Africa contributing to SDG 16.9 targets of 100 percent birth registration and establishment of legal identity for children, and 80 percent death registration.
· Aavailability of quality gender responsive trade statistics is vital to the   monitoring the SDGs 1, 2, 4, 5,8, 10 and 17. 
· Censuses are the main source of data for the SDGs, and hence assisting African countries in undertaking their censuses will improve their capacity to monitor and report on the SDGs.
· Social statistics will assist in monitoring the SDGs 1,2,3,4,5,6,8,10,11,16 and 17


	6. Target countries/instituions/sub-regions
	CRVS mentorship program: 	 Guinea-Bissau, Equatorial Guinea, Togo, Angola, DRC, Burkina Faso
Data & Statistics for more gender-responsive trade policies in Africa: 
 Cameroon, Kenya, Senegal, and Zimbabwe)
Census undertakings:  
Kenya, Ghana, Seychelles, Rwanda, Zambia, Zimbabwe, Mauritius, Togo, Sierra Leone, Liberia, Nigeria, Senegal, Namibia, and Burundi
Poverty Measurement:  		Zimbabwe, Zambia, Uganda, Tanzania and Cote d”Ivoire
Capacity Building for Gender Statistics and Monitoring Systems (CB-GenSMS): 
			Burundi, Mozambique, South Sudan, and Zimbabwe
Legal ID: 	Cameroon; Cote d’Ivoire; Democratic Republic of Congo (DRC); Kenya; Liberia; Mozambique; Sierra Leone Zambia. Ethiopia; Guinea Conakry, Niger; Nigeria and Senegal.


	7. Planned result area 1/Outcome
	RA2: Enhanced capacities of  member  States  to  develop  and  implement  integrated geospatial  information  frameworks

	8. Indicator of Achievement (IoA)
	IoA 1: Number of  countries  developing  and  implementing  national  action  plans  on  an integrated  geospatial  information  framework  (cumulative )Agenda 2063 
· Baseline (end of 2022): 16[footnoteRef:5] [5:  Benin, Burkina Faso, Cameroon, Central African Republic, Congo, Eswatini, Ethiopia, Lesotho, Madagascar, Mozambique, Morocco, Niger, Nigeria, Rwanda, Senegal, South Africa, Tunisia.] 

· Target (2023): 3[footnoteRef:6] [6:  ??? GIMS] 

· Cumulative Target= 19  (baseline (16 ) + annual target (3 ) 

	9. Deliverables, Gender marker, Quarter, Funding source)
	Deliverable[footnoteRef:7] [7: ] 

(Specify the core function: TT, Convening, OP in a parenthesis)
 
	Gender marker (0-3) 
	To be completed by
(shed the cell)
	Funding source
(not in figures)


	
	
	
	Q1
	Q2
	Q3
	Q4
	RB
	XB
	RPTC
	DA

	1
	Parliamentary documentation
	
	
	
	
	
	
	
	
	

	
	1.1. (Think Thank) Geospatial information management to the Regional Committee of United Nations Global Geospatial Information Management for Africa at its eighth and ninth meetings
	1
	
	
	
	X
	X
	
	
	

	
	1.2. (Think Thank) Integration of geospatial and statistical data to the Statistical Commission for Africa at its seventh and eighth meetings
	0
	
	
	X
	
	X
	
	
	

	2
	Substantive services for meetings
	
	
	
	
	
	
	
	
	

	
	2.1. (Convening) 13th Session of United Nations Committee of Experts on Global Geospatial Information Management;
	1
	
	
	X
	
	X
	
	
	

	
	2.2. (Convening) United Nations Group of Experts on Geographical Names
	1
	
	
	
	X
	X
	
	
	

	
	2.3. (Convening)Ninth Session of the Regional Committee of the United Nations Global Geospatial Information Management for Africa
	2
	
	
	X
	
	X
	
	
	

	3
	Field and technical cooperation projects
	
	
	
	
	
	
	
	
	

	
	3.1. (Operations) On developing geospatial information services in support of the implementation and tracking of the Sustainable Development Goals
	1
	
	
	
	X
	X
	
	
	

	
	3.2. (Operations) On guidelines for the implementation of the Integrated Geospatial Information Framework
	1
	
	
	
	X
	X
	
	
	

	
	3.3. (Operations) On strengthening the capacities of member States for the implementation of the African Geodetic Reference Frame
	1
	
	
	
	X
	X
	
	
	

	4
	Seminars, workshops and training
	
	
	
	
	
	
	
	
	

	
	2.1. (Convening) Workshop on geospatial datasets for monitoring Sustainable Development Goals for national mapping agencies and statistical offices (5).
	1
	
	X
	
	
	X
	
	
	

	
	2.2. (Convening) Workshops on the strategy for the integration of statistical and geospatial information for national mapping agencies and statistical offices (5).
	1
	
	
	X
	
	X
	
	
	

	
	2.3. (Convening) Training events on the development of national action plans on the Integrated Geospatial Information Framework for national mapping agencies
	1
	
	
	X
	
	X
	
	
	

	
	2.4. (Convening) Training events on geospatial knowledge infrastructure with innovative geospatial responses and solutions for a post-pandemic recovery
	2
	
	
	X
	
	X
	
	
	

	3
	Publication
	
	
	
	
	
	
	
	
	

	
	3.1. (Think Thank) UN-GGIM: Africa | Regional Activities report on geospatial information management in Africa
	1
	
	
	
	X
	X
	
	
	

	
	3.2. (Think Thank) Geocoding: A Strategic Pathway to the Modernization of Geospatial Information in Africa
	N/A
	
	
	X
	
	X
	
	
	

	
	3.3. (Think Thank) Assessment on the Availability of Geospatial Datasets for the Sustainable Development Goals in Africa
	N/A
	
	X
	
	
	X
	
	
	

	4
	Technical materials
	
	
	
	
	
	
	
	
	

	
	4.1. (Operational) African regional geospatial databases, online services and geoportals (1).
	N/A
	
	
	
	X
	X
	
	
	

	
	4.2. (Operational) African atlas of spatial statistics
	N/A
	
	
	
	X
	
	
	
	

	5
	Consultation, advice and advocacy
Advisory services and technical support
	
	
	
	
	
	
	
	
	

	
	5.1. (Operational) Technical assistance in the establishment of national and regional spatial data infrastructures (NSDI) and integrated geospatial information framework (IGIF)
	2
	
	
	X
	
	X
	
	
	

	
	5.2. (Operational) Technical assistance in the integration of geospatial and statistical information, the implementation of the African Geodetic Reference Frame, the development of fundamental geospatial datasets themes and standards
	1
	
	
	X
	
	X
	
	
	

	
	5.3. (Convening) | (Think Thank) | (Operations)) Technical assistance and advisory services in the implementation of global and regional initiatives and programmes (Group on Earth Observations, African initiative under the Global Earth Observation System of Systems, Global Monitoring for Environment and Security programme, Regional Centre for Mapping of Resources for Development, African Regional Institute for Geospatial Information Science and Technology, Digital Earth Africa and others)
	1
	
	
	
	X
	X
	
	
	

	6
	Databases and substantive digital material
	
	
	
	
	
	
	
	
	

	
	6.1. (Operations) Geospatial databases, online applications, services and platforms; Africa Geoportal.
	NA
	
	
	
	X
	X
	
	
	

	7
	Outreach programmes, special events and information materials
	
	
	
	
	
	
	
	
	

	
	7.1. (Convening) Geographic Information Systems Day
	1
	
	
	
	X
	X
	
	
	

	Additional narratives for each planned result/outcome

	8. SDG tagging
	· The integration of geospatial and statistical data is crucial for many of the environmental indicators of the Sustainable Development Goals (SDGs 13, 14, 15), as well as for the disaggregated analysis of socioeconomic indicators of the Sustainable Development Goals (SDGs 1, 2, 3, 4, 9, 11). In addition, the point is made that a large number of those indicators require geospatial data, and more than two-thirds are able to be visualized spatially at various subnational scales.

	9. Target countries/institutions/sub-regions
	Target Countries: 	All African countries. 
Partners:	African Union Commission, UN-GGIM, Regional Centre for Mapping of Resources for Development, African Regional Institute for Geospatial Information Science and Technology


	10. Planned result area 1/Outcome
	RA3: Enhanced capacity of member States to transform and modernize  their statistical systems Proposed  programme  plan  for 2023

	11. Indicator of Achievement (IoA)
	IoA 1: Number of member States that have implemented the road map on transformation and modernization of official statistics.
· Baseline (end of 2022):8[footnoteRef:8] [8:  2 from EIAS and 6 from SDDIOS] 

· Target (2023):8[footnoteRef:9]  [9:  To be shared between EIAS?? and SDDIOS??] 

Cumulative Target= 16 ((baseline (8) + annual target (8)

IoA 2: number of member States that have adopted and applied the 2008 System of National Accounts for the compilation of economic statistics and national accounts, including environmental-economic accounting: 
· Baseline (end of 2022): 33[footnoteRef:10] [10:  Benin, Burkina Faso, Burundi, Cameroon, Côte d'Ivoire, Djibouti, Egypt, Ghana, Guinea-Bissau, Kenya, Lesotho, Liberia, Mauritania, Mauritius, Morocco, Mozambique, Namibia, Niger, Senegal, Seychelles, Somalia, South Africa, South Sudan, Tanzania, The Gambia, Togo, Uganda, Zambia, and Zimbabwe, Central African Republic, Cabo Verde,  Congo, Democratic Republic of Congo, Equatorial Guinea, Eswatini, Seychelles, Burundi, Central Africa Republic, Congo Republic, Eswatini, Gabon, Namibia, Sao Tome and Principe, and Senegal] 

· Target (2023): -38
· Cumulative target (38) = Baseline (33) + Annual target (5[footnoteRef:11]) [11:  Central Africa Republic, Republic of the Congo, Democratic Republic of the Congo, Seychelles, Sudan, The Gambia, and Zambia] 



	12. Deliverables, Gender marker, Quarter, Funding source)
	Deliverable[footnoteRef:12] [12: .] 

(Specify the core function: TT, Convening, OP in a parenthesis)
 
	Gender marker (0-3)
	To be completed by
(shed the cell)
	Funding source
(not in figures)


	
	
	
	Q1
	Q2
	Q3
	Q4
	RB
	XB
	RPTC
	DA

	1
	Parliamentary documentation
	
	
	
	
	
	
	
	
	

	
	1.1. (Think tank) Report on statistical development in Africa 
	2
	X
	
	
	
	X
	
	
	

	
	1.2. (Think-tank) Road map on transformation and modernization of official statistics in Africa
	N/A
	
	
	
	X
	X
	X
	X
	

	
	1.3. (Think-tank) Report on SDGs indicators in Africa
	2
	
	
	X
	
	X
	X
	X
	

	
	1.4. (Think-tank) Report on implementation of census monitoring dashboard in African countries 
	2
	X
	X
	X
	
	X
	X
	X
	

	2
	Seminars, workshops, and training
	
	
	
	
	
	
	
	
	

	
	2.1. (Convening) Meeting of the Bureau of Statistical Commission for Africa (8)
	2
	X
	
	
	
	X
	
	
	

	
	2.2. (Convening)Workshop on SDGs data reporting and management  
	2
	
	
	X
	
	
	X
	X
	X

	
	2.3. (Convening)Workshop on Data science and Big Data 
	2
	X
	
	
	
	
	X
	X
	X

	
	2.4. (Convening) Data validation workshop for the African Statistical Yearbook
	2
	
	X
	
	
	X
	
	
	

	
	2.5. (Convening) Workshop to validate the report on the use of administrative data for statistical purposes in Africa
	0
	X
	
	
	
	
	X
	
	

	
	2.6. (Convening) Webinar on the Dissemination and statistical literacy using new media: how, advantages and challenges?
	0
	X
	
	
	
	
	X
	
	

	
	2.7. (Convening) Webinar on administrative data for statistical purposes
	0
	
	X
	
	X
	
	X
	
	

	
	2.8. (Convening) National workshops on integrating administrative data in statistical production
	0
	X
	X
	X
	X
	
	X
	
	

	
	2.9. (Convening) Workshop on the road map for the transformation and modernization of official statistics in Africa – cross-fertilization with other global and regional initiatives
	0
	X
	
	
	
	
	X
	
	

	
	2.10. (Convening) Regional seminar on the new system of national accounts (beyond GDP, surveys for GDP rebase, SUT/TiVA, etc.)
	0
	X
	X
	X
	X
	X
	
	
	

	
	2.11. (Convening) Regional seminar on agriculture statistics
	0
	
	
	X
	
	
	X
	
	

	
	2.12. (Convening) Regional seminar on energy statistics
	0
	
	X
	
	
	
	X
	
	

	
	2.13. (Operational Advisory expert group meeting on national accounts
	0
	
	
	
	X
	X
	
	
	

	
	2.14. (Convening) Training events on methods of environmental statistics and environmental economic accounting for national agencies responsible for the compilation of environmental economic accounts (SEEA-CF, SEEA-ecosystem, etc.)
	0
	X
	X
	X
	X
	X
	
	
	

	
	2.15. (Convening) Consultative meeting on strengthening and harmonization of economic statistics in Africa
	0
	
	
	
	X
	
	X
	
	

	
	2.16. (Convening) Expert group meeting on environmental-economic accounting 
	0
	
	
	
	X
	X
	
	
	

	3
	Publication
	
	
	
	
	
	
	
	
	

	
	3.1. (Think-tank) African Statistical Yearbook 2022
	2
	X
	X
	X
	
	
	
	
	

	
	3.2. (Think-tank) African Pocket Book 2022
	2
	
	X
	X
	X
	
	
	
	

	
	3.3. (Think-tank)Africa Statistics Flash
	2
	X
	X
	X
	X
	
	
	
	

	
	3.4. (Think tank) Report on the use of administrative data for statistical purposes in Africa.
	0
	
	X
	
	
	
	X
	
	

	
	3.5. (Think-tank) ECA Price Watch Centre: Update, analysis, and dissemination
	
	
	X
	
	X
	X
	
	
	

	
	3.6. (Think-tank) An on-line repository: “ECA Price Watch Centre”: Data in the portal are updated on a monthly basis
	0
	X
	X
	X
	X
	
	
	
	

	
	3.7.  (Think-tank)Compendium of intra-African and foreign trade statistics
	0
	
	X
	
	
	X
	
	
	

	4
	Technical materials
	
	
	
	
	
	
	
	
	

	
	4.1. (Think-tank)(ECAStats
	1
	
	
	X
	
	
	X
	
	

	
	4.2. (think-tank) African UN data for Development 
	1
	
	
	X
	
	
	X
	
	

	
	4.3. (Convening)Census Monitoring Dashboard 
	1
	
	
	X
	
	
	X
	
	

	
	4.4. (Convening) Performance Data Management System 
	1
	
	
	X
	
	
	X
	
	

	
	4.5. (Operational) Guidelines for integrating the road map for the transformation and modernization of official statistics in the NSDSs
	0
	
	
	X
	
	
	X
	
	

	5
	Advisory services and technical support
	
	
	
	
	
	
	
	
	

	
	5.1. (Operational) Digital population and housing censuses
	2
	X
	X
	X
	X
	X
	
	
	

	
	5.2. (Operational) Data science capacity building  
	0
	
	
	X
	X
	X
	X
	X
	X

	
	5.3. (operational) SDGs data management 
	2
	X
	X
	X
	X
	X
	X
	X
	X

	
	5.4. (Operational) Use of administrative data for statistical purposes
	0
	X
	X
	X
	X
	
	X
	
	

	
	5.5. (Operational) on the development of supply-use tables (SUTs), intra-regional input-output table (IOT) and trade-in-value-added (TiVA) model   
	0
	X
	X
	X
	X
	X
	
	
	

	
	5.6.  (Operational) on technical assistance on GDP updating and rebasing in member States 
	0
	X
	X
	X
	X
	X
	
	
	

	
	5.7. (Operational) on leading African countries to participate in the global updating and related testing of the 2008 SNA programme 
	0
	X
	X
	X
	X
	X
	
	
	

	
	5.8.  (Operational) on consumer price index (CPI): data collection, compilation, and application
	0
	X
	
	X
	X
	
	
	
	

	
	5.9. (Operational) Development of a data science campus 
	0
	
	
	X
	
	
	X
	
	

	Additional narratives for each planned result/outcome

	13. SDG tagging
	· The sub-programme will support censuses undertaking which are important sources of SDGs indicators. Assessment of SDGs indicators data availability and progress made by members on SDGs indicators will be part of the planned accomplishments. The sub-programme will therefore contribute to all SDGs.
· Economic and environmental statistics domains are concerned by almost all SDGs Goals and Targets. The most important ones include SDG goal 2(b) and 2(a) through increasing evidence based agricultural and rural statistics and economic statistics aimed at ending hunger and improving food security and its value chain.

	14. Target countries/instituions/sub-regions
	· ECA is planning technical assistance to 5 countries[footnoteRef:13] on digitalization and integration of data science initiatives: survey methodology and coordination of the national statistical system and statistical legislation (including administrative data systems and other sources) and technical assistance and advisory services to 5[footnoteRef:14] national statistical offices on SDGs dashboards. Three additional countries[footnoteRef:15] will be supported in integrating administrative data in statistical production. [13:  (Burkina, Cameroon, Morocco, Djibouti, Malawi]  [14:   (Benin, Equatorial Guinea, Tunisia, Ethiopia, Zimbabwe)]  [15:  Cameroon, Uganda, and a third to define.] 

· Target countries to support for using administrative data for statistical purposes: Burundi, Cameroon, Lesotho, Namibia, Togo, Uganda,
· Technical or online assistance and advisory services on GDP Rebasing programme : Republic of the Congo, Democratic Republic of the Congo, Eswatini, Gabon, Sao Tome and Principe. 
· Leading African countries to participate in the global updating and related testing of the 2008 SNA programme: All countries
· Development of supply-use tables (SUTs), intra-regional input-output table (IOT) and trade-in-value-added (TiVA) model: Eswatini, Namibia and all countries with SUT available
· TiVA project, technical assistance, and advisory services: Cameroon, Cote d’Ivoire, Egypt, Nigeria, and Senegal.
· Consumer price index (CPI): 	All countries

	Additional narratives at subprogramme level

	15. Strategic directions 
		☒   1. Build
The subprograms aims to building the capacity of MS in improving agricultural and rural statistics, Economic statistics and National Account and environmental statistics for compiling environmental economic accounting
	☒  2. Formulate
	☐  3. Design
The subprogram will design Trade in Value Added data base as part of improving capacity. Strengthening database: NA, CPI and inflation, Agriculture, Energy and SUTs

	☐  4. Integrate
	☒  5. Advocate
Advocate MS on strengthening and harmonization of economic statistics in Africa




	16. Medium term programme framework

	Indicate the alignment of the programme of work of the subprogramme to one or more of the MTPF transformation areas
	☐   1. An Africa that invests in human potential for sustainable development
	☐  2. An integrated Africa
	☒  3. An innovative, connected Africa
	☐  4. An Africa of sustainable, productive industries and economies
	☐  5. An Africa of stable and effective institutions




	17. Joint delivery

	
Thematic cluster:                Thematic cluster 5: Data, statistics and digital transformation; 
Area of Collaboration:         technical assistance to 5 countries on digitalization and integration of data science initiatives; survey methodology and coordination of the national statistical system and statistical legislation (including administrative data systems and other sources) and technical assistance and advisory services to 5 national statistical offices on SDGs dashboards
Collaborating SPs:              SROs, National statistical Offices

Thematic cluster 1: Trade and Regional Integration;
Area of collaboration: A Capacity-Building Programme on Trade in Value Added (TiVA) jointly by ECA, OECD and WTO to support member States to strengthen national accounts and balance of payments and to compile TiVA database and indicators.
Collaborating SPs: RITD, SRO-CA

Thematic cluster 2: Macro-modelling for sustainable development planning;
Area of collaboration: ECA Price Watch Center (PWC) to provide latest prices statistics on all African countries and price aggregates for country groupings, to analyze the trends and changes on emerging thematic areas, and to present and disseminate the findings and results.
Collaborating SPs: MGD, PSDFD, TCND, PGSPD, SROs 
On the use of alternative methods to collect price data: INSEE-France, ONS-UK, SurveyCTO, and UNSD


	18. Resident Coordinator System and RCP/O/IBCs and task forces
	18.1. Resident Coordinator System:
· The RC and UCTs will have three roles: to co-ordinate with ECA and pilot countries and provide administrative and logistic support for regional conferences and technical assistance missions to countries; working together with the technical team of ECA, to help provide the technical guidance for the countries to carry out the project; and to monitor the progress of project implementation in countries.

18.2. Opportunities and Issue Based Coalitions:
OIBC1: support to implementation of the UN Africa data and statistics strategy and operationalization of the Africa UN Data for Development Platform. 
· “Strengthened integrated data and statistical systems for sustainable development” This will be done through harmonizing the very concepts, definitions and classifications used across statistical sources, following national and international standards. The harmonization process shall have a unreserved contribution to ease the regional collaboration and platforms in the process of collecting and utilizing statistical data across the continent 
· on integrated data and statistical systems for sustainable development and the Africa We Want
OIBC 4 – Leveraging new technologies and enabling digital transition


	19. Partnerships 
	· Implementation of the 2008 SNA in Africa; working with the AGNA: AUC, AfDB, AFRISTAT, RECs, UNSD
· Capacity building programme on supply and uses tables ( SUTs) and Trade in value added (TiVA): jointly carried out together with OECD and WTO; and Office for National Statistics, UK contributes to technical assistance activities; 
· Capacity building programme on CPI data collection: Various international organizations and development partners to provide technical expertise and share with practical experiences (INSEE France, ONS UK, SurveyCTO, Global Partnership) 
· ECA Price Watch Centre (PWC): ECA’s substantive Divisions and RSOs
· GDP rebasing missions and update programme of SNA carried out by ECA along with other partners (AFRISTAT, AfDB, IMF, RECS, UNSD and World Bank) and the countries coordinated the intervention of different partners.  
· Contribution Agreement EU/Eurostat/UNECA on Support to monitoring of SDGs and statistics in Africa
· UNFPA on the implementation of Censuses. UNICEF, UNDESA, and UNDP on the coordination of the United Nations Legal Identity Agenda
· UN Women on Gender Statistics
· AUC and AfDB on the Conference of Ministers Responsible for Civil Registration

	20. Risks and risk responses
	      
	Risk
	Risk category[footnoteRef:16] [16:  Risk Category - All risks identified have to be classified in one of the following seven categories as per the ERM risk catalogue. i.e. (i)) Strategic, (ii) Governance (iii) Managerial (iv) Operations (v) Financial (vi) Compliance and (vii) Fraud and Corruption.] 

	Cause of the risk
	Impact description of the risk[footnoteRef:17] [17:  Impact description: This describes the effects of the risk on (i) Safety and security, (ii) Operations (iii) Reputation (iv) Financial,] 

	Risk assessment[footnoteRef:18] [18:  Risk assessment – For each risk identified, rate the probability and the impact on scale of 1-5. Refer to the probability and impact risk calculators.  The overall risk rating is obtained by multiplying the probability and impact of each risk. 
] 

	Risk treatment and response plan
	Action parties
	Timelines for implementation of treatment plans

	
	
	
	
	Probability
(1-5)
	Impact
(1-5)
	Overall risk rating
	
	
	

	Low political commitment in support of economic and environmental statistics and accounts
	Strategic
	Arousing political interest
	Countries inability to evolve policies
	4
	4
	High
	Sensitization at the high-political level
	Member States
	Throughout the year

	Lack of financial and adequate human resources to deliver the set outputs  
	Strategic/operations 
	Lack of clarity in priorities
	Planed deliverables will not be achieved
	4
	3
	Major
	Strengthen coordination and collaboration with RECs, RCs, and UNCTs to enhance project delivery and collaboration.
	ACS 
	At beginning of year and throughout 

	Lack of coordination of national statistical systems. 

	Governance/strategic 
	Inadequate engagement of Member states in project and programme design.
	Delay in program deliverables 
	1
	5
	moderate
	Increase awareness and advocacy on coordination of national statistical systems; Continuous dialogue and engagement with Member States to better assist them in their needs
	Member States
	Throughout the year

	Low level of resource mobilization in support of countries request for technical assistance
	Financial /Strategic/Governance 

	Changes by Member States during course of forming agreements resulting in low political commitment in countries of implementation
	Delay in technical assistance and there by delay in targeted outputs
	4
	4
	High
	Advocacy on resources mobilization and Strengthen coordination and collaboration with RECs, RCs, and UNCTs to enhance project delivery and collaboration.
	Member States, NSO, 
	Throughout the year


 

	21. Gender considerations 
	
Gender will be mainstreamed in all processes of collecting, managing, and analysing economic, social and demographic data. Statistical indicators will be disaggregated by gender. 

	22. Disability inclusion
	
	☒   0. Does not substantially contribute to the rights of persons with disabilities and disability inclusions but persons with disabilities benefits from the outputs
	☒  1. Contributes to the rights of persons to the rights of persons with disabilities and disability inclusion in a significant way
	☐  2. Rights of persons with disabilities and disability inclusions are the principal or primary objective of the work of the SP





	23. ES Compact
	To be completed once the draft for the 2023 compact indicators are identified.
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