# UNITED NATIONS ECONOMIC COMMISSION FOR AFRICA

## Weekly Division Update

Division/Section: 	African Centre for Statistics

Reporting Period: 	5-11 January 2026

Submitted by: 		Samuel Kobina Annim, Director, African Centre for Statistics

Date Submitted:              12th January 2026

| KPI Area | Target / Milestone | Progress This Week | Status (🟢/🟡/🔴) | Remarks |
| --- | --- | --- | --- | --- |
| IoA 1.1 (i) Number of members of ECA having adopted and applied the recommended international standards and methodology (2008 System of National Accounts and extensions) in economic statistics (cumulative) (PPB 2026) Baseline (end of 2025): 46 Annual target (2026): 1 Cumulative target (47) = Baseline (46) + annual target (1) |  |  |  |  |
| Indicator (i) Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) PPB 2026 Baseline (end of 2025): 11 Annual target (2026): 14 Cumulative target (14) = Baseline (11) + annual target (3) |  |  |  |  |
| RA: Progress towards integrated geospatial information frameworks IoA 1: Number of members of ECA applying at least one of the strategic pathways of the United Nations Integrated Geospatial Information Framework (cumulative) |  |  |  |  |
| Draft: (i) Number of ECA member States that have produced innovative statistical products for use in policy formulation, monitoring dissemination -Non PPB Baseline (end of 2025): 0 Annual target (2026): 8 Cumulative target (8 ) = Baseline ( 0) + Annual target (8) |  |  |  |  |

### 2. Major Initiatives & Projects in previous week)

| Initiative / Project | Key Milestone This Week | Next Steps | Lead Officer |
| --- | --- | --- | --- |
| Eastern Africa Regional Statistics Program-for-Results | No update | Follow up for potential DLIs | Joseph |
| Digital Censuses | Reaching out to development partners to support the acquisition of tablets for the Lesotho Census |  | William Molla |
| Migration of GIS: infrastructure to the cloud | No update |  | Peter Njagi Meron Kinfemichael Meazanesh Asres |
| Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) project | No update |  | Andre Nonguierma |
| UN-PDF call for proposals | Refining the concept paper | Submission to PRMS | Eileen, Ayenika Godheart Andre Nonguierma |
| Google project | No update | No update | Molla |
| Specialized Technical Group on Classification Training Workshop on classifications | Planning meeting | - Draft Provisional agenda - Draft Concept Note - Meeting with UNSD and AU-STATAFRIC | Ali |

3. Missions

| Team Member(s) | Destination | Dates | Objective | Key Outcomes | Funding Source (RB / RPTC / XB) |
| --- | --- | --- | --- | --- | --- |
| None |  |  |  |  |  |

### 4. Workshops / Conferences Conducted

| Title | Date / Venue | Objective | Outcome / Follow-up |
| --- | --- | --- | --- |
| None |  |  |  |

### 5. Analytical Work (Ongoing or Completed)

| Topic | Status | Strategic Relevance | Expected Output Date |
| --- | --- | --- | --- |
| Daily Statistical facts and figures | On going | - Supports the modernization of statistical dissemination and enhances visibility of African data within the ECA | Ongoing |
| Analytical work on African Statistical Yearbook - ASYB | On going | - Contributes to evidence-based policymaking through comprehensive analysis and harmonized continental statistics | March 2026 |
| Informal cross border trade | On going | - Enhances understanding of regional trade dynamics and supports AfCFTA monitoring and regional integration. | June 2027 |
| Development of Compendium for Disaster-related Statistics | Ongoing | - Updating and refining the compendium with the hazard list - Harmonizes the indicators and provides a standardized framework for monitoring, reporting, and managing disaster risks across sectors | March 2026 |
| CRVS Applied Research and Training | Ongoing | - Identifying barriers to universal vital events registration | December 2026 |
| AfCIOT | Ongoing | - Data preparation for the integration of four additional countries: Kenya, Mauritania, Niger and Uganda - Preparation of the work plan for 2026 | February 2026 |
| Monitoring Water Resources of Africa | Ongoing - Time series analysis of Lake Chad extent | - Monitoring water resources in Africa is ongoing. - Timeseries analysis of Lake Chad extent was conducted using Google Earth Engine - Time series analysis of water bodies is vital to show long-term trends and seasonal patterns in water resources, enabling policymakers and managers to understand changes over time. It informs decision-making across environmental, socio-economic, and geopolitical dimensions. | Ongoing |
| Map Production, Spatial Analysis and Printing | Ongoing | - Strengthening Evidence-Based Policy and Decision-Making | Ongoing |
| ECA Web-Based Rapid Mapping tool | Ongoing – Draft stage | - The tool will enable ECA staff and member-country experts to visualize spatial data without specialized GIS software or skills. Unlike other rapid mapping tools like Power BI or excel which lack the UN standardized basemap, this tool ensures UN standardized outputs. The app is designed for quick, professional map preparation, especially for presentations and reports. | January 31, 2026 |
| Literature review of publications and information sources for monitoring investment trends in Africa | On going | - provides an evidence-based foundation to identify, analyze, and monitor investment trends in Africa, informing policy decisions, programme design, and alignment with continental and global development agendas. | January 31, 2026 |
| Preparation of the end or programme narrative and financial reports of the EU grant to ECA. | On going | - Ensures accountability, transparency, and compliance with donor requirements while demonstrating results achieved and the effective use of resources. | January 31, 2026 |

### 6. Flagship Publications / Reports

| Title |  | Type | Status | Expected Launch / Submission |
| --- | --- | --- | --- | --- |
| 2024 Africa SDGs Progress Report: Is Africa on track to achieve the 2030 Goals? |  | Flagship Report | In progress | January 2026 |
| The 2026 Economic Report for Africa (ERA) – Chap 4, Data – The new oil fueling frontier technologies | Flagship Report | A data quality review of the ERA was conducted. Updated the chapter, taking into account the DES comments | Already submitted, and waiting for further comments to be considered |
| Preparation of ECA contributions to Africa Common positions - 57th UNSC |  | Report | In progress - Common position being drafted and country nomination to lead Africa’s position in the various sessions being identified. | January 2026 |
| Note of ACS for MFGD and other divisions on trade statistics |  | Short note | In progress Update the Draft note in preparation | 15 January 2026 |

### 7. Grants & RPTC progress

| Title of project | Type (Grant/ DA/ RPTC) | % Of resource utilization | Expiry date |
| --- | --- | --- | --- |
| - Support to Eritrea and South Sudan - Enhancing Statistical Capacity: Togo GDP Rebasing Project 2025 (Phase 1) IO-11605200 | RPTC | 99.7% | Dec 2025 (Expired) |
| DA 14 Project: 2225A - Resilient and agile national statistical systems to meet post-COVID-19 data needs to recover better | DA | 98.5% | 31st December 2025 (Expired) |
| DA 15 Project: 2326D - Quantifying South-South cooperation to mobilize funds for the Sustainable Development Goals | DA | 68.7% | June 30, 2026 |
| AfDB Grant - Capacity Building for Gender Statistics and Monitoring Systems (CB-GenSMS) Grant # S1-32HDM-000226 | XB | 94.7% | 31 December 2025 (Expired – NCE under discussion) |
| Bloomberg Grant (1) - To improve collection of birth and death data systems in Africa Grant # S1-32HDM-000247 | XB | 73.8% | 31 March 2027 |
| EAC - Eastern Africa Regional Statistics Program-for-Results (EARSP-for-R) Grant # S1-32HDM-000254 | XB | 69.2% | June 2027 |
| UNPDF - Integrated regional platform for the innovative use of Earth Observations technology for the production and validation of crop statistics (ESTELLA) Grant # S1-32HDM-000274 | XB | 0% | 30 September 2028 |
| Bloomberg Grant (2)- Developing Africa E-CRVS Shared Asset for Improvement of Digitalization of CRVS System in Africa Grant # S1-32HDM-000277 | XB | 7.7% | 30 June 2027 |
| UNFIP - Advancing data integration, innovation, and capacity in Africa (Africa Google Data Commons) Grant # S1-32HDM-000280 | XB | 8.9% | 30 June 2027 |

### 8. Key Challenges & Mitigation Measures

| Challenge | Implication | Proposed Solution / Action |
| --- | --- | --- |
| None |  |  |

9.  Member States Request

| Member State | Date Received | The Request Made | Is the request being considered? | Status Update | Additional Remarks |
| --- | --- | --- | --- | --- | --- |
| None |  |  |  |  |  |

10. Other Noteworthy Developments; Insert narrative bullet points on high-impact items, strategic engagements, resource mobilization updates, or inter-agency collaboration

None